## Staffing plan
Staffing and budgeting plan
|  | Q1 |  |  | Q2 | Q2 |  | Q3 |  |  | Q4
Person | Category | January | February | March | April | Mai | June | July | August | September | October | November | December
NN1 | Manag / Req. | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
NN2 | Manag / Req. |  | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
NN3 | Integration / Test |  |  | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
NN4 | Integration / Test |  |  | 8 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
NN5 | Integration / Test | 8 | 8 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
NN6 | Dev | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
NN7 | Dev | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
NN8 | Dev | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
NN9 | Dev |  | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
NN10 | Dev |  |  | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
NN11 | Dev |  |  | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
NN12 | Dev |  |  |  | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
NN13 | Dev |  |  |  | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
NN14 | Dev | Q2 Mai: 17; Q2 June: 17; Q3 July: 17; Q3 August: 17; Q3 September: 17; Q4 October: 17; Q4 November: 17
NN15 | Dev | Q2 Mai: 17; Q2 June: 17; Q3 July: 17; Q3 August: 17; Q3 September: 17; Q4 October: 17
| Days per month | 76 | 110 | 178 | 221 | 255 | 255 | 255 | 255 | 255 | 255 | 238 | 221
| PM / Budgets | Q1 February: 364000; Q2 Mai: 731000; Q3 August: 765000; Q4 November: 714000
| Man. / Dev / Total PM | 8.4118 | 13 | 21.4118 | 15 | 28 | 43 | 15 | 30 | 45 | 15 | 27 | 42
Labor rates |  | Q1 February: Estimated costs
Min | 800 | Q1 February: Average no. persons; Q2 April: 12.5
Max | 1200 | Q1 February: Work days per year; Q2 April: 204
Average | 1000 | Q1 February: Average cost; Q2 April: 2550000
|  |  | Budgeted cost |  | 2574000
Notes:
This is only a theoretical staffing and budgeting plan. Labor rates as well as availability of staff might vary.