## Summary
Modeling Platform Requirement |  | Relevant Exisiting Eclipse Projects | Requirement Effort for 1.0M1 [PM] | Requirement Effort for 1.0M2 [PM] | Requirement Effort for 1.0M3 [PM] | Requirement Effort for 1.0 [PM] | P1 .. P3 Requirement Effort [PM] | P4 .. P5 Requirement Effort [PM] | Total Requirement effort for 2011 [PM] | Total requirement effort [PM] | Corresponding Modeling Platform Services | Comments | Available in Sphinx Initial Contribution
Imported Effort Budgets (see Staffing and Budgeting Plan A.1.xls for details) |  |  | 13 | 28 | 30 | 27 |  |  | 152
Overall Project Execution | [8 empty] | 151.9 | 1231.475
I. Management | [8 empty] | 24.5 | 198.625
II. Platform integration | [8 empty] | 4.9 | 39.725
III. Integration testing | [8 empty] | 24.5 | 198.625
IV. Development |  |  | 13 | 28 | 30 | 27 | 77.5 | 16 | 98 | 794.5
0. Platform architecture |  |  | 4.5 | [5 empty] | 4.5 | 4.5
A. Model Version Management (Life-cycle Support) |  |  | 6.5 | 24 | 30 | 23 | 71.5 | 12 | 83.5 | 290
1. Managing versions on various model granularity, meta-model and instances |  |  | 1 | 9 | 15 | 6 | 31 | 0 | 31 | 62
1.1 a)+E-Config-1 | Versioning of metamodels and instances | CDO MTF Sphinx GMF | 1 | 9 | 4 | 0 | 14 | 0 | 14 | 22 | Version Management |  | Indirectly via Eclipse team support and external SCM system
1.1 b)+E-Config-1 | Ability to specify granularity of versions and which objects are to be versioned | CDO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Version Management |  | Indirectly through organizing model objects in resources
1.2 a) | Support of muli-user and distributed development teams | CDO Sphinx Mylyn | 0 | 0 | 8 | 6 | 14 | 0 | 14 | 18 | Version Management |  | Indirectly via Eclipse team support and external SCM system
1.2 b) +E-Config-1 | Branching of model instances | CDO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | Version Management |  | Indirectly via Eclipse team support and external SCM system
1.3 + E-Config-1 | Support for different model repository types | Sphinx MTF CDO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | Persistence |  | Only file-based SCM systems so far
Use Case + E-Comp-2 | Identification of conflicting changes/support for interactive conflict resolution | CDO Sphinx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Version Management |  | Via Eclipse team support and EMF Compare integration
Use Case + E-Collab-1 | Support for tracking, describing, annotating, reporting of model changes | CDO Sphinx BIRT | 0 | 0 | 3 | 0 | 3 | 0 | 3 | 6 | Commands & Complex Operations, Persistence, Version Management | Not explicitly mentioned in architecture | no
2. Analysis of model changes |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.5
2.1 a) | Automatic tracking and reporting of changes between two different versions (-> states) of a model | EMF Transaction EMF Compare Sphinx BIRT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | Commands & Complex Operations |  | no
2.1 b) | File output describing the model change issued when user-definable change patterns occur | Sphinx BIRT Xtext | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | Commands & Complex Operations | Not explicitly mentioned in architecture | no
Use Case | Automatic detection when model has changed and generated artifacts are out of sync; regeneration of affected artifacts | Sphinx Xtext | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | Workflow & Build Support |  | no
3. Merging of different models and versions of models |  |  | 3 | 8.5 | 6 | 14 | 25.5 | 6 | 31.5 | 108.5
3.1 a) + E-Comp-1 | Parallel work on different parts of a model and merge of resulting changes into a common model | EMF Compare/Merge Sphinx | 3 | 8.5 | 6 | 4 | 21.5 | 0 | 21.5 | 37.5 | Compare & Merge |  | Via Eclipse team support and EMF Compare integration
3.1 b) + E-Comp-1+E-Comp-2 | Automatic detection of inconsistencies in merged model and decorations identifying those | EMF Compare | 0 | 0 | 0 | 4 | 0 | 4 | 4 | 4 | Validation |  | only on demand detection so far
3.2 + E-Comp-1+ E-Comp-2 | Support merge of concrete (graphical or textual) syntax and abstract syntax (semantics) | EMF Compare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | Compare & Merge |  | only support for abstract syntax so far
Use Case | Support of automatic bulk merge operations | EMF Compare Sphinx | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 3 | Compare & Merge |  | yes
E-Comp-1+ E-Comp-2 | Support for filtering changes | EMF Compare Sphinx | 0 | 0 | 0 | 2.5 | 2.5 | 0 | 2.5 | 2.5 | Compare & Merge
E-Comp-1+ E-Comp-2 | API support for integrations | EMF Compare Sphinx | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 1.5 | 1.5 | Compare & Merge
4. Change analysis to identify root cause and impact analysis for changes to all levels of model content |  |  | 0 | 2 | 0 | 1 | 0 | 3 | 3 | 5
4.1 | Visualization of implicit and explicit impacts of model changes on other models |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Commands & Complex Operations | See "5. Traceability to identify connections between model elements, Use Case" | no
4.2 | Link of change request to resulting model changes | Mylyn Sphinx CDO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | Traceability Task Repository Interface | Not explicitly mentioned in architecture Alternative 1: Direct link | no
|  |  | 0 | 2 | 0 | 1 | 0 | 3 | 3 | 3 |  | Not explicitly mentioned in architecture Alternative 2: Link via repository | no
4.3 | Support for different external change request systems | Mylyn | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Task Repository Interface |  | no
5. Traceability to identify connections between model elements |  |  | 0 | 0 | 8 | 0 | 8 | 0 | 8 | 56
5.1 a) | Creation of relationships between model elements that are independent of their metamodel(s) | Sphinx Yakindu-Requirements | 0 | 0 | 4 | 0 | 4 | 0 | 4 | 4 | Traceability |  | no
5.1 b) | Visualization of these relationships and traceability between model elements | Yakindu-Requirements | 0 | 0 | 4 | 0 | 4 | 0 | 4 | 4 | Traceability |  | no
5.2 | Specification of such relationships in high level models and stepwise refinement in lower level models with traceability at any of those levels | Yakindu-Requirements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | Traceability | Not explicitly mentioned in architecture | no
5.3 and E-CdGen-5 + E-Doc-2 | Traceability between model elements and non-model artifacts | Yakindu-Requirements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | Traceability |  | no
Use Case | Reflection of model changes in connected model elements or artifacts (notifier/listener service) | EMF Transaction Sphinx Yakindu-Requirements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Commands & Complex Operations Traceability |  | no
5.4 (proposed) | Support of upcoming OMG ReqIF standard (orginiating from existing RIF standard, metamodel for expressing and exchanging requirements) | Sphinx Yakindu-Requirements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | Exemplary Tools | To be mentioned in architecture | no
6. Support for meta-model change and update to appropriate instances |  |  | 2.5 | 4.5 | 1 | 2 | 7 | 3 | 10 | 41
6 a) | Support for automatic application of metamodel changes to model instances | CDO Sphinx | 0 | 4 | 1 | 2 | 4 | 3 | 7 | 7 | Metamodel Management | Alternative 1: Extensible Model Converter service | To some extent through serialization level model converters
|  | EAdapt Ecore Tools Sphinx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 |  | Alternative 2: Automatic migration based on metamodel change description | To some extent through serialization level model converters
6 b) | Indication which metamodel changes are possible and which are not | Ecore Tools EMF Validation Sphinx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | Metamodel Management |  | no
6 c) | Support for different versions of a metamodel in the same environment | Sphinx | 2.5 | 0.5 | 0 | 0 | 3 | 0 | 3 | 3 | Metamodel Management |  | yes
6 d) | Selective migration of model instances to a new version of the metamodel | EMF Core CDO Sphinx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | Metamodel Management |  | To some extent through serialization level model converters
Use Case | Automatic/transparent upgrade of old model instances to newer metamodel version |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Metamodel Management |  | To some extent through serialization level model converters and model save management
Use Case | Evalutation of differences between metamodel versions |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Compare & Merge |  | To some extent, via EMF Compare integration
B. Model Audit Support |  |  | 0 | 0 | 0 | 4 | 0 | 4 | 4 | 23
1. Overall end-to-end lifecycle management/model governance (elements can be in different 'review' states) |  |  | 0 | 0 | 0 | 4 | 0 | 4 | 4 | 17
1.1 a) | Support of review cycles and approvals | Mylyn | 0 | 0 | 0 | 4 | 0 | 4 | 4 | 11 | Task-focused Modeling & Auditing Task Repository Interface |  | no
1.1 b) | Ability to record who has done review/given approval | Mylyn | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Task-focused Modeling & Auditing Task Repository Interface Access Control | To be mentioned in architecture | no
1.1 c) | Ability to specify who needs review/approve and can see related model elements | Mylyn | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Task-focused Modeling & Auditing Task Repository Interface Access Control | To be mentioned in architecture | no
1.2 a) | Support of definition of users and roles | Mylyn | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | Identity Management Interface |  | no
1.2 b) | Support for different external authentication and user management systems | Mylyn Sphinx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Identity Management Interface |  | no
2. Quality checks for models |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
2.1 | Support for doing and recording quality checks during model life cycle |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Traceability Access Control |  | no
Use Case | Review of specific model fragments and freezing of those model fragments when done | Sphinx CDO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | Task-focused Modeling & Auditing Access Control | To be mentioned in architecture | no
Use Case | Promotion/Review of content and limited visibility | CDO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Task-focused Modeling & Auditing | To be mentioned in architecture | no
E-Anal-1 | Ability to invoke model analysis tools | Eclipse Platform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Analysis Tool Interface | Why is OCL/EMF Validation needed here? | no
E-Anal-2 | Ability to configure analysis tool from within authoring tool | Eclipse Platform | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Analysis Tool Interface | Why is OCL/EMF Validation needed here? | no
C. Core Platform Features for Enterprise Use |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Support for large models, including lazy loading, partial collection handling | [8 empty] | 0 | 0
1.1 a) | Support for models containing 500 000+ model objects | any | [6 empty] | 0 | 0 |  | Non-functional requirement | yes
1.1 b) | Tools built on MP scale to large models (e.g., diagram editors) | any | [6 empty] | 0 | 0 |  | Non-functional requirement | yes
Use Case | 300 000 model objects in 7000 resources | any | [6 empty] | 0 | 0 |  | Non-functional requirement | yes
Use Case | 60 000 changes recordable in versioning system | any | [6 empty] | 0 | 0 |  | Non-functional requirement | Indirectly via external SCM system
Use Case | 3000 sequence diagrams, 450 MB file size | any | [6 empty] | 0 | 0 |  | Non-functional requirement | Tested with models with up to 100 MB file size
Use Case | 200 000 model objects and 900 000 references | any | [6 empty] | 0 | 0 |  | Non-functional requirement
2. Ability to work offline and then merge changes back into a model | [8 empty] | 0 | 0
2.1 | Support for extraction of partial view of model from repository and reintegration of updated view | [7 empty] | 0 | 0 | Persistence | To be mentioned in architecture | Only for models from file-based SCM systems via Eclipse team support and EMF Compare integration so far
2.2 a) | Tools built on MP must be usable without network connection | any | [6 empty] | 0 | 0 |  | General requirement/theme, not related to a specific service in architecture | yes
2.2 b) | Extracted partial model view must be usable offline | [7 empty] | 0 | 0 | Persistence | To be mentioned in architecture | Only for models from file-based SCM systems so far
3. Support for modeling standards and open formats. Lowest denominator is the EObject (Ecore) | [8 empty] | 0 | 0
3.1 | All MP services must support any metamodel implementation based on EObject/Ecore | any | [6 empty] | 0 | 0 |  | General requirement/theme, not related to a specific service in architecture | yes
4. End-to-End project support from business architecture to code and testing | [8 empty] | 0 | 0
4.1 a) | Support for different types of models during different steps of the software development lifecycle | [7 empty] | 0 | 0 | Metamodel Management |  | yes
4.1 b) | Traceability/impact analysis across different types of models | [7 empty] | 0 | 0 | Commands & Complex Operations Traceability |  | no
D. Flexible Content Support |  |  | 2 | 4 | 0 | 0 | 6 | 0 | 6 | 362
1. General purpose models based on industry standards like UML, BPMN and SysML |  |  | 2 | 4 | 0 | 0 | 6 | 0 | 6 | 203
1.1 a) | Out of the box support of industry standards UML, BPMN and SysML | Papyrus UML2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | Exemplary Tools | Alternative 1: UML profile for BPMN | Examplary out of the box support for UML
|  | BPMN GMF, Graphiti EMF Validation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 |  | Alternative 2: BPMN tools for native BPMN DSL
E-Auth-1 | Support for the full UML 2 standard | Papyrus UML 2 EMF Core Sphinx CDO MXF | 2 | 4 | 0 | 0 | 6 | 0 | 6 | 77 | UML IDE |  | no
E-Auth-2 | Support for the UML 2 profile mechanism | Papyrus UML2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | UML IDE, Generic Model Views |  | no
E-Auth-3 | OCL language support | OCL Papyrus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | Validation |  | no
E-Auth-6 | Support for the OMG standard MARTE profile | Papyrus UML 2 OCL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | UML IDE, Validation |  | no
E-Auth-7 | Support for the OMG standard SysML profile | Papyrus UML 2 OCL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | UML IDE, Validation |  | no
E-Auth-8 | Support for the UML Action Language standard | Xtext(?) JDT(?) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | Editor Management |  | no
E-Auth-9 | Support for the UML RT profile | Papyrus UML 2 OCL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
E-Auth-10 | Rhapsody UML profile | Papyrus UML 2 OCL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
1.1 b) | Capacity to extend support to any other modeling standard | any | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | General requirement/theme, not related to a specific service in architecture | yes
2. Domain Specific Models | [8 empty] | 0 | 0
2.1 | All MP services must be applicable to user-defined domain specific modeling languages | any | [6 empty] | 0 | 0 |  | General requirement/theme, not related to a specific service in architecture | yes
2.2 | Support for definition DSLs, handling of DSL instances, validation of DSL instances against corresponding DSL definition | any | [6 empty] | 0 | 0 |  | General requirement/theme, not related to a specific service in architecture | yes
3. M2M Transformations | [8 empty] | 0 | 110
3.1 | Support for creation of new model transformation templates, update of existing ones, and testing for validity | ATL Sphinx EFacet | [6 empty] | 0 | 15 | Transformation |  | no
|  | QVTo Sphinx EFacet | [6 empty] | 0 | 16
|  | Xtend/MWE Sphinx EFacet | [6 empty] | 0 | 10
3.2 a) | Ability to select and apply appropriate model transformation template to one or several models | ATL Sphinx EFacet | [6 empty] | 0 | 9 | Transformation Workflow & Build Support | To be mentioned in architecture | no
|  | QVTo Sphinx EFacet | [6 empty] | 0 | 7
|  | Xtend/MWE Sphinx EFacet | [6 empty] | 0 | 9
3.2 b) | Capability to obtain transformation result and related information (e.g., error log) | ATL Sphinx EFacet | [6 empty] | 0 | 2 | Transformation Workflow & Build Support | Not explicitly mentioned in architecture | no
|  | QVTo Sphinx EFacet | [6 empty] | 0 | 2
|  | Xtend/MWE Sphinx EFacet | [6 empty] | 0 | 2
3.2 c) | Support for potentially required annotation of source model; availability of suitable annotation capabilities in model authoring tools | ATL Sphinx EFacet | [6 empty] | 0 | 8 | Metamodel Management | Not explicitly mentioned in architecture | no
|  | QVTo Sphinx EFacet | [6 empty] | 0 | 8
|  | Xtend/MWE Sphinx EFacet | [6 empty] | 0 | 10
3.2 d) | Support of semi-automatic transformation enabling users to interactively guide transformation engine as needed | ATL Sphinx EFacet | [6 empty] | 0 | 4 | Transformation Workflow & Build Support | To be mentioned in architecture | no
|  | QVTo Sphinx EFacet | [6 empty] | 0 | 4
|  | Xtend/MWE Sphinx EFacet | [6 empty] | 0 | 4
4. Model to Text (M2T) Transformations |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49
4.1 + E-Doc-1 | Support for generation of source code, documentation and test cases from a model | Acceleo Sphinx | [6 empty] | 0 | 12 | Code Generation Transformation Document & Report Generation |  | no
|  | BIRT Sphinx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
|  | Xpand/MWE Sphinx | [6 empty] | 0 | 11
4.2 (proposed) | Ability to select and apply appropriate generation template to one or several models | Acceleo Sphinx | [6 empty] | 0 | 8
|  | BIRT Sphinx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Xpand/MWE Sphinx | [6 empty] | 0 | 6
E-CdGen-1 | Open, modifiable, and extensible code generation specifications | Acceleo Sphinx | [6 empty] | 0 | 0 | Code Generation Transformation Editor Management |  | no
|  | BIRT Sphinx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Xpand/MWE Sphinx | [6 empty] | 0 | 0
E-CdGen-2 | Ability to generate code for different target languages | Acceleo Sphinx | [6 empty] | 0 | 0 | Code Generation Transformation Editor Management |  | no
|  | BIRT Sphinx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Xpand/MWE Sphinx | [6 empty] | 0 | 2
E-CdGen-4 | Ability to define incremental and scalable code generators and compilations | Acceleo Sphinx | [6 empty] | 0 | 0 | Workflow & Build Support |  | no
|  | BIRT Sphinx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Xpand/MWE Sphinx | [6 empty] | 0 | 0
E-CdGen-6 | Code generation support for easy debugging of generated code | Acceleo Sphinx | [6 empty] | 0 | 0 | Code Generation Traceability (?) | We need to understand what current tools provide for this (if anything) and also investigate how 3GLs deal with this problem | no
|  | BIRT Sphinx | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Xpand/MWE Sphinx | [6 empty] | 0 | 0
E. Governance |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42
1. Tracking and managing project status | [8 empty] | 0 | 0
1.1 | Ability to define which project information is to be tracked and how it is to be reported | [7 empty] | 0 | 0 | Monitoring & Tracking |  | no
1.2 a) | Capability to determine current status of key project indicators | [7 empty] | 0 | 0 | Monitoring & Tracking |  | no
1.2 b) | Capability to determine how those evolved over time (project history) | [7 empty] | 0 | 0 | Monitoring & Tracking |  | no
1.2 c) | Support for raising warnings when certain critical situations or events occur | [7 empty] | 0 | 0 | Monitoring & Tracking |  | no
2. Toolset configuration and management | [8 empty] | 0 | 42
2.1 | Support for constitution and configuration of new tools suites for use by a team or enterprise | MTF P2 Sphinx | [6 empty] | 0 | 28 | Provisioning |  | no
2.2 | Support for adding new tools/capabilities to existing tools suites | MTF P2 Sphinx | [6 empty] | 0 | 2 | Provisioning |  | no
2.3 | Support for controlled update of individual tools/capabilities in existing tools suites | MTF P2 Sphinx | [6 empty] | 0 | 12 | Provisioning |  | no
F. Host and Target Debugging |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73
E-CdGen-3 | Support code generation and debugging on different target platforms | MXF | [6 empty] | 0 | 24 |  |  | no
E-DbgSim-1 | Model-level simulation with debug support | MXF | [6 empty] | 0 | 24 | Simulation & Debug | To be added to architecture | no
E-DbgSim-2 | Debug of individual instances (vs just classes) | MXF | [6 empty] | 0 | 6 | Simulation & Debug | To be added to architecture | no
E-DbgSim-3 | Store and restore of debug/test harnesses | MXF | [6 empty] | 0 | 9 | Simulation & Debug | To be added to architecture | no
E-Dbg-Sim-4 | Simulation/execution trace record and replay | MXF | [6 empty] | 0 | 10 | Simulation & Debug | To be added to architecture | no

## A1. VersionManagement
Requirement | [5 empty] | OpenSource Tool(s) Evaluated | Criteria |  |  |  | Total Estimated Gap Effort [PM] | Potential Developer Group | Requirement Effort for 1.0M1 [PM] | Requirement Effort for 1.0M2 [PM] | Requirement Effort for 1.0M3 [PM] | Requirement Effort for 1.0 [PM] | P1 .. P3 Requirement Effort [PM] | P4 .. P5 Requirement Effort [PM] | Total Requirement Effort for 2011 [PM] | Total Requirement Effort [PM]
Category | Requirement Name | Req. Id | Priority | Target Milestone | Detailed capability |  | Functionality |  | Documentation
[7 empty] | Discussion | Est. Effort[PM] | Discussion | Est. Effort[PM]
A. Model Version Management (Life-cycle Support) 1. Managing versions on various model granularity, meta-model and instances | Versioning of metamodels and instances | 1.1 a)+E-Config-1 | 1 | 1.0M1 | Versioning of a model | CDO MTF Sphinx GMF | [CDO] Supported, but capacity to label/tag committed changes still missing (currently only commit number is exposed) | 1 |  | 0 | 1 | itemis, Eike Stepper | 1 | 9 | 4 | 0 | 14 | 0 | 14 | 22
|  |  | 1 | 1.0M2 | User interface for mapping models from one or several CDO repositories to projets in the workspace and navigating through them (includes CDO Repository Exploring perspective with CDO Repositories view and other related views, Project Explorer displaying workspace projects and mapped model resources and elements inside, actions for creating new model resources and elements, opening model resources and elements in editors, etc.) |  | [CDO] Examplary implementations of CDO Repository Exploring perspective and Project Explorer integration available [Sphinx] Provides required UI support for file-based models which can be enhanced to support models from repositories; however up to now the Sphinx platform relies on EMF Transaction ResourceSetListeners, i.e., adapters that listen to changes of the complete model, which need to be customized or substituted by a CDO compatible change listener service as to avoid performance and memory leak problems; requires functionality from "A6. Migration/Support for different versions of a metamodel in the same environment" 6c | 4 |  | 1 | 5 | Geensys
|  |  | 2 | 1.0M3 | User interface for inspecting and managing model versions (includes History view, action contributions to Eclipse "Replace With" context menu, etc.) |  | Not supported; [CDO or Sphinx] Should be added as new feature | 3 |  | 1 | 4 | Geensys, itemis, Eike Stepper
|  |  | 1 | 1.0M2 | User interface for inspecting differences between 2 model versions on same branch (includes 2-point Compare view/editor operating on a single change set, corresponding action contributions to Eclipse "Compare With" context menu, etc.) |  | Not supported; [CDO or Sphinx] Should be added as new feature | 3 |  | 1 | 4 | Geensys, itemis, Eike Stepper
|  |  | 30 |  | Capability to automatically include concrete (graphical or textual) syntax when versioning abstract syntax (semantics) |  | [CDO] Supported for GMF-based graphical syntax provided that a CDO-compatible Ecore implementation is made available and GMF Notation metamodel uses it; mainly covered by "D1. Standards Support / Support for the full UML 2 standard" E-Auth-1; some additional effort required for integrating CDO-compatible Ecore implementation with GMF [CDO] Not supported for textual syntax; difficult to achieve because of non-model-based nature of whitespace information in textual models and different approaches to handling object identity in textual modeling and model repositories; not further analyzed here as it seems that textual modeling is not a high priority in the context of this study | 1 |  | 0 | 1
|  |  | 30 |  | Versioning of tool components that are compatible with certain metamodel version ranges |  | [MTF] Not supported yet but planned in the scope of this project; should be implemented as an extension of the P2 provisioning service | 2 |  | 0 | 2
|  |  | 30 |  | Automatic proposal and installation/update of tool components that fit the metamodel version behind models upon checkout |  | [MTF] Not supported yet but planned in the scope of this project; should be implemented as an extension of the P2 provisioning service; also requires an extensible capability to detect metamodel version behind models in SCM system or model repository; default implementation gets it from namespace of XML files or EPackages registered in CDO repository; applications must be enabled to contribute custom detectors through an extension point (e.g. for reading the metamodel version from a properties file) | 3 |  | 1 | 4
|  |  | 20 |  | User feeback if version of metamodel implementation included/used by tools is inconsistent wrt models being handled in workspace |  | Sphinx | 1 |  | 0 | 1
| Ability to specify granularity of versions and which objects are to be versioned | 1.1 b)+E-Config-1 | 30 |  | Versioning of complete models | CDO | N/A at repository level; can potentially be achieved through filtering/compacting object level versioning information in the UI; impossible to provide an effort estimate without deeper knowledge of the use case; should be investigated based on some concrete use case at a later point in time | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 30 |  | Versioning of model fragments (e.g., a model object and its containments) |  |  | 0 |  | 0 | 0
|  |  | 30 |  | Capability to define and apply patterns of model fragments to be versioned together |  |  | 0 |  | 0 | 0
|  |  | 1 |  | Versioning of individual model objects |  | [CDO] Supported | 0 |  | 0 | 0
|  |  | 30 |  | Versioning of sets of related model fragments (i.e., model fragments which are not directly referencing eachother but are anyway related, e.g. in terms of tracability) |  | Requires a more detailed investigation based on some concrete use case prior to providing meaningful effort estimates | 0 |  | 0 | 0
[19 empty] | 10 | 18
| Support of muli-user and distributed development teams | 1.2 a) | 1 |  | Support for retrieve/submit models to a repository on a remote machine | CDO Sphinx Mylyn | [CDO] Supported | 0 |  | 0 | 0 |  | 0 | 0 | 8 | 6 | 14 | 0 | 14 | 18
|  |  | 1 | 1.0M3 | Capability to define user profiles |  | Not supported; [CDO] A default implementation for a server-side user management module should be made available | 3 |  | 1 | 4 | itemis, Eike Stepper
|  |  | 1 | 1.0M3 | Capability to define users and associate them with profiles | [5 empty] | ?
|  |  | 2 | 1.0 | Capability to retrieve existing user and user profile definitions from external user management systems (e.g., LDAP, Active Directory) |  | Not supported; [CDO] Should be added as new feature | 3 |  | 1 | 4 | itemis, Eike Stepper
|  |  | 30 |  | Eclipse client for administrating users and user profile definitions in external user management systems (e.g., LDAP, Active Directory) |  | Not supported; [Mylyn or Sphinx] Should be added as new feature | 3 |  | 1 | 4
|  |  | 1 | 1.0M3 | Capability to associate user profiles with access priviledges, i.e., to define which kind of changes on which parts of a model the users of each profile are allowed to do |  | Not supported; [CDO or Sphinx] Some sort of access control meta model should be defined which can be instantiated in the repository and used to define which object types and/or which object instances on which branch users associated with a given user profile are allowed to access; an adequate user interface for authoring such access control models (e.g. form editor, properties view, etc.) should be provided along with that | 3 |  | 1 | 4 | Geensys, itemis, Eike Stepper
|  |  | 1 | 1.0M3 | Capability to authenticate users when they connect to model repository, i.e., to identify them through an interactive or automated login process |  | [CDO] Partially supported through possibility to contribute a server-side user manager; [CDO] Should be extended by a default implementation for such a user manager; effort estimate included in "Capability to define user profiles...", see above | 0 |  | 0 | 0
|  |  | 1 | 1.0M3 | Capability to authorize users when they read/write the repository, i.e., to approve or deny the part of the model they attempt to access and the kind of change they are about to do according to their associated user profile |  | [CDO] Partially supported through generic service for application-defined read/write access hooks which can intercept and approve/reject each access; [CDO or Sphinx] A default implementation for such a hook which approves/denies read/write access attempts based on above mentioned access control model should be added; effort estimate included in "Capability to associate user profiles...", see above | 0 |  | 0 | 0
|  |  | 1 |  | Capability to work in connected (online) mode enabling instant check-in of own changes and instant feedback about changes/conflicts created by other users working on same repository |  | [CDO] Supported | 0 |  | 0 | 0
|  |  | 1 |  | Capability to work in disconnected (offline) mode including support for later check-in of changes/feedback of changes from other users |  | [CDO] Supported | 0 |  | 0 | 0
|  |  | 1 | 1.0 | Support of usual Eclipse team workflow operations (including Team Synchronizing perspective and Synchronize view, action contributions such as commit, update, override, etc.) when working in disconnected (offline) mode |  | Not supported; [CDO or Sphinx] Should be added as new feature; can partially reuse user inferface features identified in "Versioning of metamodels and instances", see above | 1 |  | 1 | 2 | Geensys, itemis, Eike Stepper
| Branching of model instances | 1.2 b) +E-Config-1 | 1 |  | Branching a complete models | CDO | Supported | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
|  |  | 10 |  | User interface for inspecting and merging differences between 2 model versions on different branches (includes 3-point Compare/Merge view/editor operating on 2 change sets with a common ancestor version, 4-point Compare/Merge view/editor operating on 2 change sets with different ancestor versions, corresponding action contributions to Eclipse "Compare With" context menu, etc.) |  | Not supported; [CDO or Sphinx] Should be added as new feature; requires a more detailed analysis of the exact workflows to be supported | 5 |  | 1 | 6
|  |  | 30 |  | Branching of model fragments (e.g., a model object and its containments) |  | N/A at repository level; can potentially be achieved through filtering/compacting object level versioning information in the UI; impossible to provide an effort estimate without deeper knowledge of the use case; should be investigated based on some concrete use case at a later point in time | 0 |  | 0 | 0
|  |  | 30 |  | Branching of individual model objects |  |  | 0 |  | 0 | 0
|  |  | 30 |  | Branching of sets of related model fragments (i.e., model fragments which are not directly referencing eachother but are anyway related, e.g. in terms of tracability) |  | Requires a more detailed investigation based on some concrete use case prior to providing meaningful effort estimates | 0 |  | 0 | 0
| Support for different model repository types | 1.3 + E-Config-1 | 1 |  | Support for model repositories (i.e., databases) | Sphinx MTF CDO | [CDO] Supported | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
|  |  | 1 |  | Support for file repositories (i.e., conventional SCM systems) |  | [Sphinx] Supported | 0 |  | 0 | 0
|  |  | 30 |  | Capability to retrieve/submit models from different repository types in parallel |  | Needs to be analyzed once repository types other than CDO have been identified; no reasonable effort estimate possible before that | 0 |  | 0 | 0
|  |  | 20 |  | Capability to manage projects containing models and non-model resources (e.g., source code, documentation, etc.) |  | [CDO] Not supported yet but could be covered through leaf nodes that complement existing resource nodes containing model objects and could be used for storing binary/text files; [CDO or Sphinx] Corresponding user interface support needs to be added; effort 3 PM implementation + test, 1 PM documentation [MTF] Draft implementation of MFT server which automatically versions non-model artifacts on SCM system and model artifacts on repository available; currently based on SVN and Teneo; needs to be genereralized such as to support other SCM systems and CDO; also needs to be thoroughly tested; effort 3 PM implementation + test, 2 PM documentation | 6 |  | 3 | 9
| Identification of conflicting changes/support for interactive conflict resolution | Use Case + E-Comp-2 |  |  | Graphical display of changes | CDO Sphinx | See "Versioning of metamodels and instances (1.1 a)+E-Config-1)" | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  | 20 |  | Graphical display of conflicts |  | [CDO] Partially supported when working in connected (online) mode; some improvements in terms of usability should be made [CDO or Sphinx] When working in disconnected (offline) mode conflicts should be indicated by label decorator in Synchronize view of Team Synchronizing perspective; effort estimate included in "Support of usual Eclipse team workflow operations...", see above | 1 |  | 0 | 1
|  |  | 1 |  | Support for manual merge and conflict resolution |  | [CDO] Supported when working in connected (online) mode; [CDO or Sphinx] When working in disconnected (offline) mode, a 3-point Compare/Merge view/editor operating on local change set in the workspace and remote change set on the server is required; effot estimate included in "User interface for inspecting and merging differences between 2 model versions on different branches...", see above | 0 |  | 0 | 0
| Support for tracking, describing, annotating, reporting of model changes | Use Case + E-Collab-1 | 1 | 1.0M3 | Traceability of the actions of users on the models | CDO Sphinx BIRT | [CDO] Not supported; along with each commit the change set and the user having done it need to be stored; possibility of querying all commits done by a certain user, or similar things need to b provided; [CDO or Sphinx] Corresponding user interface support must be included | 2 |  | 1 | 3 | Geensys, itemis, Eike Stepper | 0 | 0 | 3 | 0 | 3 | 0 | 3 | 6
|  |  | 10 |  | Tracking changes with respect to bug tracking |  | See "A4. Change analysis to identify root cause and impact analysis for changes to all levels of model content / Link of change request to resulting model changes (4.2)" | 0 |  | 0 | 0
|  |  | 10 |  | Generation of reports of model changes |  | Not supported; [Sphinx] Should be added as new feature; could leverage functionality provided by "D4. M2T-BIRT" to generate different kinds of reports from CDO change sets (e.g., report listing the details of one change set, report listing the change sets and commit comments for all changes done by a given user, etc.); adequate user interface support for configuring and running report generation also required | 2 |  | 1 | 3

## A2. ChangeTracking
Requirement | [5 empty] | OpenSource Tool(s) Evaluated | Criteria |  |  |  | Total Estimated Gap Effort [PM] | Potential Developer Group | Requirement Effort for 1.0M1 [PM] | Requirement Effort for 1.0M2 [PM] | Requirement Effort for 1.0M3 [PM] | Requirement Effort for 1.0 [PM] | P1 .. P3 Requirement Effort [PM] | P4 .. P5 Requirement Effort [PM] | Total Requirement Effort for 2011 [PM] | Total Requirement Effort [PM]
Category | Requirement Name | Req. Id | Priority | Target Milestone | Detailed capability |  | Functionality |  | Documentation
[7 empty] | Discussion | Est. Effort[PM] | Discussion | Est. Effort[PM]
A. Model Version Management (Life-cycle Support) 2. Analysis of model changes | Automatic tracking and reporting of changes between two different versions (-> states) of a model | 2.1 a) | 10 |  | Abiltity to record model changes when model is modified in the workspace and provide them in the form of change descriptions | EMF Transaction EMF Compare Sphinx BIRT | [Sphinx] Partially supported through EMF Transaction ResourceSetListeners; however need to check if it can be used in conjunction with CDO without suffering from performance and memory leak problems; potentially requires some adaptations or a separate service implementation for CDO; could benefit from results of "A1 Version Management / Versioning of metamodels and instances / User interface for mapping models..." in that case | 2 |  | 0 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5
|  |  | 10 |  | Automatic update of change descriptions in case of undo/redo operations
|  |  | 10 |  | Automatic persistence and reset of change descriptions when model is saved
|  |  | 10 |  | View that enables users to inspect model modifications that have been accumulated since last save including filtering to hide irrelevant changes |  | [Sphinx] Not supported; | 0.5 |  | 0 | 0.5
|  |  | 10 |  | Ability to export change desciption to file in workspace of file system |  | [Sphinx] Not supported; could be implemented by direclty exporting change descriptions recorded by EMF Transaction (i.e., using EMF Change model/XMI serialization) or by transforming them to EMF Compare EPatches and exporting those or both | 1.5 |  | 0 | 1.5
|  |  | 20 |  | Ability to generate a customizable report from a change description |  | Mainly covered by "D4. M2T-BIRT"; some extra effort for adequate user interface support for configuring and running report generation required; can reuse functionality from "A1. VersionManagement" / "Support for tracking, describing, annotating, reporting of model changes" Use Case + E-Collab-1 / "Generation of reports of model changes" for that purpose | 0.5 |  | 0 | 0.5
| File output describing the model change issued when user-definable change patterns occur | 2.1 b) |  |  | Based on "Automatic tracking and reporting of changes between two different versions (-> states) of a model" (2.1 a)) | Sphinx BIRT Xtext |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
|  |  | 10 |  | Scalable change notification and handling service supporting complex customizable filter conditions |  | Integration of scalable adapter-based change notification and handling service proposed by SAP in Sphinx (as replacement for EMF Transaction ResourceSetListeners which are used up to now) | 3 |  | 1 | 4
|  |  | 10 |  | User interface support for specifying notification filter conditions in a convenient way (i.e., using some query language, without writing Java code) |  |  | 3 |  | 1 | 4
|  |  | 10 |  | Automatic export change desciption to file in workspace or file system when notification filter condition is matched |  | Covered by "Automatic persistence and reset of change descriptions when model is saved", see above | 0 |  | 0 | 0
|  |  | 10 |  | Automatic generation of change report based on predefined custom template when notification filter condition is matched |  | Covered by "D4. M2T-BIRT" | 0 |  | 0 | 0
| Automatic detection when model has changed and generated artifacts are out of sync; regeneration of affected artifacts | Use Case |  |  | Based on "Scalable change notification and handling service supporting complex customizable filter conditions" (2.1 b)) | Sphinx Xtext |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
|  |  | 10 |  | Automatic generation of generated artifacts behind changed model elements based on predefined custom code generation templates when notification filter condition is matched |  | Requires ability to determine affected artifacts to be generated from change notification and invocation of corresponding M2M or M2T launch configuration | 2 |  | 1 | 3
|  |  | 20 |  | Integration with Eclipse incremental builder framework and enablement of concatenation model-based build steps (e.g., validation, code generation) and non-model build steps (e.g., compilation, packaging, etc.) |  | Need to extend the Eclipse Incremental Builder framework such as to trigger builds not only upon resource changes but also on model changes and to pass these model changes to the incremental builder being invoked | 1 |  | 1 | 2

## A3. CompareMerge
Requirement | [5 empty] | OpenSource Tool(s) Evaluated | Criteria |  |  |  | Total Estimated Gap Effort [PM] | Potential Developer Group | Requirement Effort for 1.0M1 [PM] | Requirement Effort for 1.0M2 [PM] | Requirement Effort for 1.0M3 [PM] | Requirement Effort for 1.0 [PM] | P1 .. P3 Requirement Effort [PM] | P4 .. P5 Requirement Effort [PM] | Total Requirement Effort for 2011 [PM] | Total Requirement Effort [PM]
Category | Requirement Name | Req. Id | Priority | Target Milestone | Detailed capability |  | Functionality |  | Documentation
[7 empty] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM]
A. Model Version Management (Life-cycle Support) 3. Merging of different models and versions of models | Parallel work on different parts of a model and merge of resulting changes into a common model | 3.1 a) + E-Comp-1 | 20 |  | Support for 3-way merge | EMF Compare/Merge Sphinx | Not supported | 12 |  |  | 12 |  | 3 | 8.5 | 6 | 4 | 21.5 | 0 | 21.5 | 37.5
|  |  | 1 | 1.0M1 | Support for 2-way merge |  | Supported; however frequent robustness problems (i.e., NullPointerExceptions etc. ) when opening CompareEditor or making merges; requires code review and/or intensive integration testing based on customer use cases | 2 | Partially supported; the capability is somewhat documented but not to the extent required for an end user to use | 1 | 3 | Obeo, Zeligsoft
|  |  | 3 | 1.0M3 | Integrated with Eclipse team component |  | [Sphinx] Partially support at model element level ("Compare With/Latest from Repository"action already available others still to be added); model element aware extension/implementation of "Synchronizing" view in "Team Synchronizing" perspective required [EMF Compare] Supported at the file level | 4 | Partially; more explicit documentation of this capability is needed | 1 | 5 | Geensys, Zeligsoft
|  |  | 20 |  | Support of different types of SCM backends |  | [Sphinx] Partially supported at model element level; some support for SVN Subversive client, CVS, ClearCase still to be added [EMF Compare] Supported at the file level provided the SCM is plugged into the Team API | 3 | Partially supported; there is no explicit documentation describing how to using an SCM | 1 | 4
|  |  | 2 | 1.0M2 | Support of model repository backends, in particular CDO |  | Not supported | 3 | Not supported | 1 | 4 | Obeo, itemis, Eike Stepper
|  |  | 1 |  | Identification of atomic changes |  | Supported | 0 | Supported | 0 | 0
|  |  | 3 | 1.0 | Identification of rule based changes |  | Partially supported; it appears as though this would be possible through the customization API, however, it could be made easier | 3 | Not supported; there does not appear to be any documentation to explain to a user how add customized rules for diff and merge | 1 | 4 | Obeo, Zeligsoft
|  |  | 1 |  | Support for user controllable merge |  | Supported; the user is able to decide whether to accept the change or not | 0 | Supported; this is documented as a standard Eclipse worklfow for the Compare editor | 0 | 0
|  |  | 3 | 1.0M2 | Comparison/merge of model elements or fragments instead of entire resources/files |  | [Sphinx] Supported | 0 | [Sphinx] Some documentation still to be added | 1 | 1 | Geensys
|  |  | 3 | 1.0M2 | Support for logical model merging |  | [Sphinx] Supported
|  |  | 2 | 1.0M2 | Support for loading minimal set of resources/files |  | Not supported; planned in Sphinx through model indexing service | 2 | Not supported | 0.5 | 2.5 | Geensys
|  |  | 3 | 1.0M2 | Operation on shared model instances in the workspace |  | [Sphinx] Supported | 0 | Some documentation still to be added | 1 | 1 | Geensys
|  |  | 3 | 1.0M2 | Model-oriented dirty state management |  | [Sphinx] Supported
|  |  | 3 | 1.0M2 | Editor-relative undo/redo contexts |  | [Sphinx] Supported
|  |  | 3 |  | Creation of rules for rule based changes |  | Partially supported; it appears as though this would be possible through the customization API, however, it could be made easier; effort estimate included in "Identification of rule based changes", see above | 0 | Not supported; there is no documentation on how to specify rule based change | 0 | 0
|  |  | 3 | 1.0M3 | Editor support for presenting changes in a tree or flat structure. Editor support for grouping changes by EClass, physical file or repository and change type |  | Not supported; the standard Eclipse compare UI does not support this at this point so it would have be added; required to be added to file-oriented Compare editor of Eclipse Platform as well as to model element aware Compare editor of Sphinx | 1 | Not supported; | 0 | 1 | Obeo, Zeligsoft, Geensys
| Automatic detection of inconsistencies in merged model and decorations identifying those | 3.1 b) + E-Comp-1+E-Comp-2 | 4 | 1.0 | Automated detection of basic conflicts | EMF Compare | [EMF Compare] Supported | 0 | Not supported; the automated conflict detection is not described in the documentation | 1 | 1 | Obeo | 0 | 0 | 0 | 4 | 0 | 4 | 4 | 4
|  |  | 5 | 1.0 | Automated detection of rule based conflicts |  | Partially supported; see identification of rule based changes | 2 | Not supported; there is no documentation on how to identify a conflicting rule based change | 1 | 3 | Obeo, Zeligsoft
| Support merge of concrete (graphical or textual) syntax and abstract syntax (semantics) | 3.2 + E-Comp-1+ E-Comp-2 | 20 |  | Graphically show in diagrams the changes | EMF Compare | Not supported | 60 |  |  | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60
| Support of automatic bulk merge operations | Use Case | 4 | 1.0 | Automated resolution of basic changes | EMF Compare Sphinx | [Sphinx] Partially; improvements based on some concrete uses cases still to be done | 1 | Some documentation still to be added | 1 | 2 | Geensys, Zeligsoft | 0 | 0 | 0 | 2 | 0 | 2 | 2 | 3
|  |  | 10 |  | Automated resolution of rule based changes |  | Not supported; could be handled in same way as for basic changes on Sphinx side | 1 |  | 0 | 1
|  |  | 10 |  | Automated merge of model elements or fragments instead of entire resources/files |  | [Sphinx] Partially; improvements based on some concrete uses cases still to be done | 0 |  | 0 | 0
|  |  | 10 |  | Operation on shared model instances in the workspace |  | [Sphinx] Supported | 0 | Some documentation still to be added | 0 | 0
|  |  | 10 |  | Model-oriented dirty state management |  | [Sphinx] Supported | 0 | Some documentation still to be added | 0 | 0
|  |  | 10 |  | Editor-relative undo/redo contexts |  | [Sphinx] Supported | 0 | Some documentation still to be added | 0 | 0
| Support for filtering changes | E-Comp-1 + E-Comp-2 | 3 | 1.0 | User interface support within editor to select filters | EMF Compare Sphinx | Not supported; requires filter service that can be easily added to file-oriented Compare editor of Eclipse Platform as well as to model element aware Compare editor of Sphinx | 0.5 |  | 0 | 0.5 | Obeo, Zeligsoft | 0 | 0 | 0 | 2.5 | 2.5 | 0 | 2.5 | 2.5
|  |  | 3 | 1.0 | Filters for different atomic and "rule based" changes/differences |  | Not supported; | 2 |  | 0 | 2 | Obeo, Zeligsoft
|  |  | 3 | 1.0 | Filters using string patterns
|  |  | 3 | 1.0 | Ability to extend/add available filters
|  |  | 3 | 1.0 | Filter selection and configuration through preferences
| API support for integrations | E-Comp-1 + E-Comp-2 | 3 |  | Public API to request a diff between to models providing the result as a list of structural differences or serialized to a file | EMF Compare Sphinx | Supported; EMF compare diff model provides this through its match/diff engine and metamodel | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 1.5 | 1.5
|  |  | 3 | 1.0 | API to create a viewer listing all structural changes resulting from a model comparison which includes the filtering and grouping options as mentioned in section above. |  | Not supported; | 0.5 |  | 0 | 0.5 | Obeo, Zeligsoft
|  |  | 3 | 1.0 | API to query the viewer for the list of visible changes (e.g. not filtered out) |  | Not supported; | 0.5 |  | 0 | 0.5 | Obeo, Zeligsoft
|  |  | 3 |  | The type of elements returned in the list of structural differences shall offer an API to retrieve the Location information of the affected elements, this in order to trigger the selection of the affected elements in Project Explorer and Editor. |  | Supported; | 0 |  | 0 | 0
|  |  | 3 |  | The type of elements returned in the list of structural differences shall offer an API to retrieve the modification type e.g. add, delete, change, move, separation/fragment, join/fragment) |  | Supported; diff/match model will contain this information | 0 |  | 0 | 0
|  |  | 3 |  | The type of elements returned in the list of structural differences shall offer an API to retrieve the Meta model class (type) e.g. Documentation, stereotype) |  | Supported; diff/match model will contain this information | 0 |  | 0 | 0
|  |  | 3 | 1.0 | API to launch an Eclipse Model Compare editor with two specified versions of model files and be able to programmatically request the selection of a structural change based on a previously obtained location. |  | Not supported; need an easier way to select the structural change; required to be added to file-oriented Compare editor of Eclipse Platform as well as to model element aware Compare editor of Sphinx | 0.5 |  | 0 | 0.5 | Obeo, Zeligsoft
Note on F4: Toby McClean: Support for merging three models where one is the common ancestor of the other two
Note on F5: Toby McClean: Support for merging two models where one of them is identified as the baseline.
Note on F6: Toby McClean: Support for the standard Eclipse team environment workflows.
Note on F7: Stephan Eberle: Integration with Eclipse Team environment must support all major SCM backends, i.e., CVS, SVN, and Git.
Note on F8: Stephan Eberle: Integration with Eclipse Team environment must support model repository backends, i.e., CDO.
Note on F9: Toby McClean: This includes basic model operations like add, change, delete, move, and reorder
Note on F10: Toby McClean: Changes that are defined by a rule to consider a set of atomic changes as a change that must be consider as one. That is, either all the atomic changes are accepted or all are rejected.
Note on F11: Toby McClean: User controllable merge allows the user to decide which changes should be merged to create the merged model without the tool doing it automatically.
Note on F12: Stephan Eberle: means that the scope of compare/merge operations is not limited to entire files or resources but can be narrowed down to composites of model elements or individual model elements. Includes the capacity to compare/merge model elements/fragments persisted in the same or different resources or files.
Note on F13: Toby McClean: means that the logical model is merged and not a fragmented physical model.
Note on F14: Toby McClean: means that only those physical files that contain changed logical model elements are actually loaded during the merge
Note on F15: Stephan Eberle: means that no new instance of the model in question is created or loaded during compare/merge operation but that it operates on a model instance that is shared with other tools in the workspace.
Note on F16: Stephan Eberle: means that merge operations being carried out on shared model instances don't set the compare/merge editor itself dirty. Instead the underlying shared model instance is set dirty and the compare/merge editor just reflects the model's dirty state. As a consequence, all other editors and views that might have been opened on the same shared model instance in parallel will become dirty at the same time.
Note on F17: Stephan Eberle: Makes sure that changes which have been done in the compare/merge editor are only visible in the undo/redo menus if this editor is active but not when switching to other views or editors operating on the same shared model instance.
Note on F18: Toby McClean: Provide some framework for expressing what a composite change is for a particular domain. That is, these rules would define what atomic changes must considered as a single change in order for the merged model to be semantically correct.
Note on F21: Toby McClean: Detection of basic changes in a 3-way merge that can not be resolved. This occurs most likely if the two models that are being merged based on the common ancestor have changed the same element. For example, changing the type of an attribute.
Note on F22: Toby McClean: Detection of composite changes in a 3-way merge that can not be resolved automatically. This occurs most likely if the two models that are being merged based on the common ancestor have changed the same element. For example, moving the same element on a diagram.
Note on F24: Toby McClean: Allow a user to visually see changes to elements on a diagram. For example the elements that have been deleted, added or moved.
Note on F28: Toby McClean: Support automatic merging of basic changes into the merged model when there is no conflict.
Note on F29: Toby McClean: Support automatic merging of composite changes into the merged model when there is no conflict. This must take into account the semantics of the composite change.
Note on F30: Stephan Eberle: means that the scope of automated merge operations are not limited to entire files or resources but can be narrowed down to composites of model elements or individual model elements. Includes the capacity to merge model elements/fragments persisted in the same or different resources or files.
Note on F31: Stephan Eberle: means that no new instance of the model in question is created or loaded during compare/merge operation but that it operates on a model instance that is shared with other tools in the workspace.
Note on F32: Stephan Eberle: means that merge operations being carried out on shared model instances don't set the compare/merge editor itself dirty. Instead the underlying shared model instance is set dirty and the compare/merge editor just reflects the model's dirty state. As a consequence, all other editors and views that might have been opened on the same shared model instance in parallel will become dirty at the same time.
Note on F33: Stephan Eberle: Makes sure that changes which have been done in the compare/merge editor are only visible in the undo/redo menus if this editor is active but not when switching to other views or editors operating on the same shared model instance.

## A4. ChangeAnalysis
Requirement | [5 empty] | OpenSource Tool(s) Evaluated | Criteria |  |  |  | Total Estimated Gap Effort [PM] | Potential Developer Group | Requirement Effort for 1.0M1 [PM] | Requirement Effort for 1.0M2 [PM] | Requirement Effort for 1.0M3 [PM] | Requirement Effort for 1.0 [PM] | P1 .. P3 Requirement Effort [PM] | P4 .. P5 Requirement Effort [PM] | Total Requirement Effort for 2011 [PM] | Total Requirement Effort [PM]
Category | Requirement Name | Req. Id | Priority | Target Milestone | Detailed capability |  | Functionality |  | Documentation
[7 empty] | Discussion | Est. Effort[PM] | Discussion | Est. Effort[PM]
A. Model Version Management (Life-cycle Support) 4. Change analysis to identify root cause and impact analysis for changes to all levels of model content | Visualization of implicit and explicit impacts of model changes on other models | 4.1 |  |  | See "5. Traceability to identify connections between model elements, Use Case" |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Link of change request to resulting model changes | 4.2 |  |  | Alternative 1: Direct link | Mylyn Sphinx CDO
[5 empty] | Based on "A2. ChangeTracking / Automatic tracking and reporting of changes between two different versions (-> states) of a model" 2.1 a) |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  |  | 10 |  | Addition of change descriptions of modified models to active Mylyn task context |  | Not supported | 2 |  | 0 | 2
|  |  | 10 |  | Capability to extract change description from active Mylyn task context |  | Not supported
|  |  | 10 |  | View that enables users to inspect model modifications that are associated with active Mylyn task context |  | Covered by "Capability to extract change description from active Mylyn task context" and "A2. ChangeTracking / Automatic tracking and reporting of changes between two different versions (-> states) of a model" | 0 |  | 0 | 0
|  |  | 20 |  | Ability to generate a customizable report for model modifications that are associated with one or serveral Mylyn task contexts selected by the user |  | Covered by "Capability to extract change description from active Mylyn task context" and "A2. ChangeTracking / Automatic tracking and reporting of changes between two different versions (-> states) of a model" | 0 |  | 0 | 0
Alternative 2: Link via model repository
|  |  | 4 | 1.0M2 | Support for Mylyn task-based change set management in model repositories, in particular CDO (i.e., sort of Mylyn SCM connector for CDO) |  | Not supported | 2 |  | 0 | 2 | itemis, Tasktop, Eike Stepper | 0 | 2 | 0 | 1 | 0 | 3 | 3 | 3
|  |  | 4 | 1.0 | Link of Mylyn task context to relevant model repository revisions |  | Not supported | 1 |  | 0 | 1 | itemis, Tasktop, Eike Stepper
|  |  | 4 | 1.0 | Capability to extract change description from differences between affected model repository revisions |  | Mainly covered by "A3. CompareMerge" and "A1. VersionManagement"; some extra effort for integration with Mylyn required
|  |  | 4 | 1.0 | View that enables users to inspect model modifications behind repository revisions that are associated with active Mylyn task context |  | Covered by "Capability to extract change description from differences between affected model repository revisions" and "A3. CompareMerge" and "A1. VersionManagement" | 0 |  | 0 | 0
|  |  | 20 |  | Ability to generate a customizable report for model modifications behind repository revisions that are associated with one or serveral Mylyn task contexts selected by the user |  | Covered by "Capability to extract change description from differences between affected model repository revisions" and "A1. VersionManagement" / "Support for tracking, describing, annotating, reporting of model changes" Use Case + E-Collab-1 | 0 |  | 0 | 0
| Support for different external change request systems | 4.3 | 1 |  | Connection to different types of task management systems (e.g., Bugzilla, Trac, JIRA, ClearQuest, Quality Center) | Mylyn | Supported | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 20 |  | Connection to different types of ALM systems (e.g., IBM, HP and Microsoft) |  | Supported by commercial Tasktop tools only; could be redeveloped in open source but only upon specific request | 0 |  | 0 | 0

## A5. Traceability
Requirement | [5 empty] | OpenSource Tool(s) Evaluated | Criteria |  |  |  | Total Estimated Gap Effort [PM] | Potential Developer Group | Requirement Effort for 1.0M1 [PM] | Requirement Effort for 1.0M2 [PM] | Requirement Effort for 1.0M3 [PM] | Requirement Effort for 1.0 [PM] | P1 .. P3 Requirement Effort [PM] | P4 .. P5 Requirement Effort [PM] | Total Requirement Effort for 2011 [PM] | Total Requirement Effort [PM]
Category | Requirement Name | Req. Id | Priority | Target Milestone | Detailed capability |  | Functionality |  | Documentation
[7 empty] | Discussion | Est. Effort[PM] | Discussion | Est. Effort[PM]
A. Model Version Management (Life-cycle Support) 5. Traceability to identify connections between model elements | Creation of relationships between model elements that are independent of their metamodel(s) | 5.1 a) | 3 | 1.0M3 | Creation of traceability relationships between two elements in a same model instance | Sphinx Yakindu-Requirements | [Yakindu-Requirements] Supported; development ongoing and first version expected in early 2011; additional effort required for industry quality implementation [Sphinx or Yakindu-Requirements] Should provide tracepoint providers supporting tracability relationships to models managed in Sphinx | 3 |  | 1 | 4 | itemis, Geensys | 0 | 0 | 4 | 0 | 4 | 0 | 4 | 4
|  |  | 3 | 1.0M3 | Creation of traceability relationships between two elements in different model instances that are based on the same metamodel
|  |  | 3 | 1.0M3 | Creation of traceability relationships between two elements in different model instances that are based on different metamodels
[19 empty] | 0 | 4
| Visualization of these relationships and traceability between model elements | 5.1 b) | 3 | 1.0M3 | Visualization of traceability relationships in same model instance | Yakindu-Requirements | Supported; development ongoing and first version expected in early 2011; additional effort required for industry quality implementation | 3 |  | 1 | 4 | itemis | 0 | 0 | 4 | 0 | 4 | 0 | 4 | 4
|  |  | 3 | 1.0M3 | Visualization of traceability relationships between different model instances that are based on the same metamodel
|  |  | 3 | 1.0M3 | Visualization of traceability relationships between different model instances that are based on different metamodels
|  |  | 3 | 1.0M3 | Support for different kinds of visualization (e.g., tree-based brower view, table-based view, graphical view, decoration/highlighting of related elements in explorer views, filtering of explorer view such that only related model elements are shown)
|  |  | 3 | 1.0M3 | Analysis of traceability relationships (e.g., listing of impacted model elements when a given model element is changed, listing of all covered/uncovered elements in a given model instance)
|  |  | 3 | 1.0M3 | Navigation between related model instances and elements (i.e. opening related model elements in editors, selecting related model elements in explorer view)
| Specification of such relationships in high level models and stepwise refinement in lower level models with traceability at any of those levels | 5.2 | 20 |  | Refinement of a traceability relationship between models into one or several traceability relationships between elements of these models | Yakindu-Requirements | Not yet planned but should be added as new feature | 2 |  | 0 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
|  |  | 20 |  | Refinement of a traceability relationship between elements of some model into several traceability relationships between other elements of the same model
|  |  | 20 |  | Refinement of a traceability relationship between elements of some model into one or several traceability relationships between elements of another model
|  |  | 20 |  | Visualization of linked traceability relationships |  | Not yet planned but should be added as new feature; can leverage and extend results from "Visualization of these relationships and traceability between model elements" 5.1 b), see above | 2 |  | 1 | 3
|  |  | 20 |  | Analysis of traceability relationships including/excluding linked traceability relationships
|  |  | 20 |  | Navigation between related models and elements including/excluding linked traceability relationships
| Traceability between model elements and non-model artifacts | 5.3 and E-CdGen-5 + E-Doc-2 | 10 |  | Creation of traceability relationships between model elements and non-model artifacts (e.g., documents, source code) or particular sections in a non-model artifacts (by adding annotations to affected model elements and non-model artifact sections) | Yakindu-Requirements | Supported for text documents, e.g., source code etc.; development ongoing and first version expected in early 2011; additional effort required for industry quality implementation | 2 |  | 1 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22
|  |  | 10 |  | Visualization of traceability relationships to non-model artifacts
|  |  | 10 |  | Analysis of traceability relationships to non-model artifacts
|  |  | 10 |  | Navigation between related model elements and and non-model artifacts or particular sections in non-model artifacts
|  |  | 10 |  | Ability to link model element to documents (HTML/XML/PDF/WORD) |  | Not supported; need to provide document format and use case specific tracepoint providers | 6 |  | 1 | 7
|  |  | 30 |  | Ability to link model element to DOORS |  | Partially supported through ReqIF import capability; substantial additional effort required if direct connection to DOORS is needed | 6 |  | 0 | 6
|  |  | 30 |  | Ability to link model element to ReqPro |  | Partially supported through ReqIF import capability; substantial additional effort required if direct connection to ReqPro is needed | 6 |  | 0 | 6
| Reflection of model changes in connected model elements or artifacts (notifier/listener service) | Use Case | 20 |  | Notification about impacts on related models and model elements when some model gets updated with changes from another user | EMF Transaction Sphinx Yakindu-Requirements | [Yakindu-Requirements] Not yet planned but should be added as new feature; can reuse change notification services provided by EMF Transaction or Sphinx | 3 |  | 1 | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
|  |  | 30 |  | Notification about impacts on related models and model elements when some non-model artifact gets updated with changes from another user |  | [Yakindu-Requirements] Not yet planned but should be added as new feature | 3 |  | 1 | 4
|  |  | 20 |  | Visalization of subset of traceability relationships that are affected by incoming model changes |  | [Yakindu-Requirements] Not yet planned but should be added as new feature; can leverage and extend results from "Visualization of these relationships and traceability between model elements" 5.1 b), see above | 2 |  | 0 | 2
| Support of upcoming OMG ReqIF standard (orginiating from existing RIF standard, metamodel for expressing and exchanging requirements) | 5.4 (proposed) | 10 |  | EMF implementation of ReqIF metamodel | Sphinx Yakindu-Requirements | [Yakindu-Requirements] Provides implementation for former RIF standard; needs to be updated when ReqIF has been released [Sphinx or Yakindu-Requirements] Integration with Workspace Management for accomodating ReqIF models in parallel to other models in the same workspace | 4 |  | 0 | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
|  |  | 20 |  | Form-based editor for authoring ReqIF models |  | [Yakindu-Requirements] Provides draft implementation for former RIF standard; needs to be updated when ReqIF has been released and improved to reach industrial quality level | 5 |  | 2 | 7

## A6. Migration
Requirement | [5 empty] | OpenSource Tool(s) Evaluated | Criteria |  |  |  | Total Estimated Gap Effort [PM] | Potential Developer Group | Requirement Effort for 1.0M1 [PM] | Requirement Effort for 1.0M2 [PM] | Requirement Effort for 1.0M3 [PM] | Requirement Effort for 1.0 [PM] | P1 .. P3 Requirement Effort [PM] | P4 .. P5 Requirement Effort [PM] | Total Requirement Effort for 2011 [PM] | Total Requirement Effort [PM]
Category | Requirement Name | Req. Id | Priority | Target Milestone | Detailed capability |  | Functionality |  | Documentation
[7 empty] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM]
A. Model Version Management (Life-cycle Support) 6. Support for meta-model change and update to appropriate instances | Support for automatic application of metamodel changes to model instances | 6 a) |  |  | Level 1: Extensible Model Converter service
|  |  | 2 | 1.0M2 | Extensible model converter service enabling model instances to be migrated forth and back between different metamodel versions; capacity to implement and contribute user-defined model converters for specific metamodel version combinations; ability to provide a human readable description of the conversion strategy for each contributed model converter | CDO Sphinx | [Sphinx] Extensible model converter service for models persisted in XML files available; converts XML elements before deserialization/after serialization; should be evolved towards a conversion of AnyType objects to model objects after loading/model objects to AnyType objects before saving | 1 |  | 1 | 2 | Geensys, itemis, Eike Stepper | 0 | 4 | 1 | 2 | 4 | 3 | 7 | 7
|  |  | 5 | 1.0 | Capacity to select a particular model converter based on its description in case that multiple model converters for the same metamodel version combination are available |  |  | 1 |  | 1 | 2 | Geensys, itemis
|  |  | 2 | 1.0M2 | Automatic application of appropriate/selected model converter when loading/saving model instances |  |  | 2 |  | 0 | 2 | Geensys, itemis
|  |  | 4 | 1.0M3 | Capacity to configure metamodel version to be used when model is saved/persisted (e.g. via workspace preferences or project properties) |  |  | 1 |  | 0 | 1 | Geensys, itemis
Level 2: Automatic migration based on metamodel change description
|  |  | 30 |  | Capability to obtain a description of the changes between two versions of a metamodel (by recording metamodel changes during authoring or by comparing two metamodel versions after authoring), and to enrich it with information as to how to automatically migrate existing instances | EAdapt Ecore Tools Sphinx | [EAdapt] Draft implementaion will be available soon; substantial additional effort required for making a useful feature out of it | 6 |  | 2 | 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22
|  |  | 30 |  | Integration with Ecore Tools for conveniently creating such change descriptions while metamodel is being authored |  | Not supported | 2 |  | 1 | 3
|  |  | 30 |  | Capability to apply enriched change descriptions to model instances with corresponding old version so as to migrate them to corresponding new version (e.g., through a model converter according to approach 1 which interprets enriched change descriptions or by generating model converters according to approach 1 from enriched change descriptions) |  | [EAdapt] Draft implementaion will be available soon; substantial additional effort required for making a useful feature out of it | 6 |  | 0 | 6
|  |  | 30 |  | Capcity to filter or disable parts of the UI corresponding to features which are supported by metamodel version used in tooling but not by that behind persistence backend (i.e., metamodel version behind format of files in SCM system or metamodel version behind database schema in model repository) and cannot be handled by automatic model instance migration facilities |  | [Sphinx] Not supported | 4 |  | 1 | 5
| Indication which metamodel changes are possible and which are not | 6 b) |  |  | Only useful when "Indication which metamodel changes are possible and which are not / Level 2: Automatic migration based on metamodel change description", see above, has been realized | Ecore Tools EMF Validation Sphinx |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
[5 empty] | Based on "2. Analysis of model changes / File output describing the model change issued when user-definable change patterns occur" 2.1 b) |  |  | 0 |  | 0 | 0
|  |  | 30 |  | Identification "unallowed" metamodel change patterns entailing incompatibilities of model instances that cannot be covered by automatic model instance migration capabilities; implementation of a set of compatibility validation constraints capable of detecting metamodel changes matching these "unallowed" metamodel change patterns while metamodel is being authored |  | Not supported | 3 |  | 1 | 4
|  |  | 30 |  | Integration with Ecore Tools for automatically applying these compatibility validation constraints when metamodel is being authored
|  |  | 30 |  | Enhancement of EMF Validation and/or integration with Sphinx for obtaining advanced visualization of compatibility validation results (e.g. through Problem view entries, label decoration of tree-based views, etc.) |  | Not supported | 3 |  | 0 | 3
| Support for different versions of a metamodel in the same environment | 6 c) | 1 | 1.0M1 | Capacity to accomodate, distinguish and access different model instances that coexist in the Eclipse workspace; ability to load, edit, and save them; support for models with different scopes of included projects and files (e.g., models that are mapped to a project and include all resources with a given type inside that project, models that are mapped to a folder in a project and include all resources with a given type inside that folder); support for adding/removing dependencies between such model instances | Sphinx | [Sphinx] Supported for file-based models; some enhancements necessary for repository-based models; need to add documentation (devopper guide in Eclipse Help) | 1.5 |  | 1 | 2.5 | Geensys | 2.5 | 0.5 | 0 | 0 | 3 | 0 | 3 | 3
|  |  | 1 | 1.0M1 | Capacity to handle such model instances being based on the same metamodel
|  |  | 1 | 1.0M1 | Capacity to handle such model instances being based on different versions the same metamodel
|  |  | 1 | 1.0M1 | Capacity to handle such model instances being based on different metamodels
|  |  | 1 | 1.0M1 | Ability to configure the version of a given metamodel to be used in a project (via project properties) and the default version of that metamodel in the workspace (via workspace preferences)
|  |  | 3 | 1.0M2 | Generic wizard for creating projects supporting a given metamodel with a user-selectable version of that metamodel |  | [Sphinx] Partially supported | 0.5 |  | 0 | 0.5 | Geensys
|  |  | 3 | 1.0M2 | Generic wizard for creating model resources corresponding to the metamodel and version which are configured on a project
| Selective migration of model instances to a new version of the metamodel | 6 d) |  |  | Based on "Support for automatic application of metamodel changes to model instances" 6 a) | EMF Core CDO Sphinx |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  |  | 10 |  | Capacity to select a model or set of model resources, choose one of potentially several applicable model converters and apply it to selected model or set of model resources |  | [Sphinx] Partially supported | 1 |  | 1 | 2
| Automatic/transparent upgrade of old model instances to newer metamodel version | Use Case |  |  | See "Support for automatic application of metamodel changes to model instances" |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0
| Evalutation of differences between metamodel versions | Use Case |  |  | See "3. Merging of different models and versions of models" |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0

## B. Auditing
Requirement | [5 empty] | OpenSource Tool(s) Evaluated | Criteria |  |  |  | Total Estimated Gap Effort [PM] | Potential Developer Group | Requirement Effort for 1.0M1 [PM] | Requirement Effort for 1.0M2 [PM] | Requirement Effort for 1.0M3 [PM] | Requirement Effort for 1.0 [PM] | P1 .. P3 Requirement Effort [PM] | P4 .. P5 Requirement Effort [PM] | Total Requirement Effort for 2011 [PM] | Total Requirement Effort [PM]
Category | Requirement Name | Req. Id | Priority | Target Milestone | Detailed capability |  | Functionality |  | Documentation
[7 empty] | Discussion | Est. Effort[PM] | Discussion | Est. Effort[PM]
B. Model Audit Support 1. Overall end-to-end lifecycle management/model governance (elements can be in different 'review' states) | Support of review cycles and approvals | 1.1 a) |  |  | Based on "A1. VersionManagement" | Mylyn |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 4 | 0 | 4 | 4 | 11
[5 empty] | Based on "A4. ChangeAnalysis / Link of change request to resulting model changes (4.2) / Alternative 2: Link via model repository" |  |  | 0 |  | 0 | 0
|  |  | 4 | 1.0 | Ability for authors to commit a change and submit corresponding Mylyn task for review |  | Not supported but planned to be started once the project restructuring of Mylyn and its evolution into a top-level project has been completed | 3 |  | 1 | 4 | itemis, Tasktop, Eike Stepper
|  |  | 4 | 1.0 | Automatic notification of reviewer(s) when a Mylyn task has been submitted for review
|  |  | 4 | 1.0 | Ability for reviewer to inspect latest change behind Mylyn task by comparing it to last approved version
|  |  | 4 | 1.0 | Ability for reviewer to approve change (e.g., by setting a flag on corresponding Mylyn task) or reject it and add some comments about the reason for that to corresponding Mylyn task
|  |  | 4 | 1.0 | Automatic notification of author(s) when a change has been approved/rejected
|  |  | 4 | 1.0 | Ability to store review related task data in underlying task repository (e.g., Bugzilla, Trac, JIRA, ClearQuest, Quality Center, etc.)
|  |  | 20 |  | Ability to enter review comments directly on/beside affected model element and have them automatically added to active Mylyn task |  | Not supported | 2 |  | 0 | 2
|  |  | 10 |  | Mylyn context bridge for EMF, i.e., integration of EMF Ecore model with the Mylyn Context degree-of-interest model |  | Not supported | 1 |  | 1 | 2
|  |  | 10 |  | Degree-of-interest highlighting and focussing for model elements in tree-based views |  | Not supported; support for regular JFace viewers as well as common navigator views should be included | 1 |  | 0 | 1
|  |  | 10 |  | Degree-of-interest highlighting and focussing for model elements in graphical editors |  | Not supported; support for GEF figures and GMF diagrams should be included | 1 |  | 0 | 1
|  |  | 20 |  | Highlighting and focussing for model elements related to review comments |  | Not supported | 1 |  | 0 | 1
| Ability to record who has done review/given approval | 1.1 b) | 10 |  | Capability to authenticate users when they connect to task repository, i.e., to identify them through an interactive or automated login process | Mylyn | Supported | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 10 |  | Capability to record which user has conducted a review (approval/rejection) on corresponding Mylyn task |  | Not supported; effort estimate included in "Support of review cycles and approvals / Ability for authors to commit a change and submit it for review...", see above | 0 |  | 0 | 0
|  |  | 10 |  | Capability to query Mylyn tasks wrt their review state (e.g., all Mylyn tasks that have been reviewed/not reviewed, reviewed/approved/rejected by a certain user, etc.)
| Ability to specify who needs review/approve and can see related model elements | 1.1 c) | 10 |  | Ability to specify the users who are entitled to do reviews when having logged in as a user with sufficient priviledges (e.g., via some review management extension to Mylyn Task Repositories view) | Mylyn | Not supported; effort estimate included in "Support of review cycles and approvals / Ability for authors to commit a change and submit it for review...", see above | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 10 |  | Capacity to authorize review-related changes on Mylyn tasks and reject such changes when a non-authorized user attempts to submit them
| Support of definition of users and roles | 1.2 a) | 30 |  | Capability to define user profiles | Mylyn | These capabilities are by nature subject to the backend task repository in use (e.g., Bugzilla, Trac, JIRA, ClearQuest, Quality Center, etc.); however Mylyn could provide some sort of user management extension, i.e., some UI support for administrating users in the backend task repository from within Eclipse | 6 |  | 0 | 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
|  |  | 30 |  | Capability to define users and associate them with profiles
| Support for different external authentication and user management systems | 1.2 b) | 30 |  | Capability to retrieve existing user and user profile definitions from external user management systems (e.g., LDAP, Active Directory) | Mylyn Sphinx | This capability is by nature subject to and in most cases supported by the backend task repository in use (e.g., Bugzilla, Trac, JIRA, ClearQuest, Quality Center, etc.) | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 30 |  | Eclipse client for administrating users and user profile definitions in external user management systems (e.g., LDAP, Active Directory) |  | Covered by "A1. VersionManagement / Support of muli-user and distributed development teams" | 0 |  | 0 | 0
B. Model Audit Support 2. Quality checks for models | Support for doing and recording quality checks during model life cycle | 2.1 |  |  | Covered by "Support of review cycles and approvals" 1.1 a), see above |  |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Review of specific model fragments and freezing of those model fragments when done | Use Case | 20 |  | Capability to select successfully reviewed model elements or fragments and mark them as final and to persist and share this information in underlying model repository | Sphinx CDO | Not supported; [CDO or Sphinx] Some sort of approval/finalization meta model should be defined which can be instantiated in the repository and used to define which object instances are marked as final; an adequate user interface for authoring such approval/finalization models (e.g. form editor, properties view, etc.) should be provided along with that | 3 |  | 1 | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
|  |  | 20 |  | Ability to specify the users who are entitled to mark model elements or fragments as final when having logged in as a user with sufficient priviledges |  | Not supported; [CDO or Sphinx] Could reuse access control meta model from "A1. Version Management / Support of muli-user and distributed development teams" to control which users have access to approval/finalization model mentioned above | 0 |  | 0 | 0
|  |  | 20 |  | Capability to authenticate users when they connect to model repository, i.e., to identify them through an interactive or automated login process |  | Covered by "A1. VersionManagement / Support of muli-user and distributed development teams" | 0 |  | 0 | 0
|  |  | 20 |  | Capacity to authorize finalization requests for model elements or fragments and reject such requests when a non-authorized user attempts to submit them |  | Covered by "A1. VersionManagement / Support of muli-user and distributed development teams" | 0 |  | 0 | 0
|  |  | 20 |  | Capability to manage access priviledges to final model elements and fragments (i.e., read-only or read-write) according to user profiles |  | Not supported; [CDO or Sphinx] Could reuse access control meta model from "A1. Version Management / Support of muli-user and distributed development teams" to define access priviledges to final model elements and fragments for users associated with a given user profile | 1 |  | 0 | 1
|  |  | 20 |  | Capability to restrict access to final model elements and fragments to read-only |  | Not supported; [Sphinx] Requires extension of editing domains to support model element level read-only accesses (currently only supported at resource level) [CDO or Sphinx] Read/write access hook for approving/denying access attempts to final model elements based on above mentioned access control model | 1 |  | 0 | 1
| Promotion/Review of content and limited visibility | Use Case | 10 |  | Capability to merge approved model changes to another branch of the model repository | CDO | Covered by "A1. VersionManagement / Branching of model instances" | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 10 |  | Capability to define and enforce individual access priviledges for each branch such as to provide personal development branches, team integration branches, and company wide publication branches |  | Covered by "A1. VersionManagement / Support of muli-user and distributed development teams" | 0 |  | 0 | 0
| Ability to invoke model analysis tools | E-Anal-1 | 1 |  | Nothing to add | Eclipse Platform | Supported by through External Tools launch configurations | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ability to configure analysis tool from within authoring tool | E-Anal-2 | 1 |  | Nothing to add | Eclipse Platform | Supported by through External Tools launch configurations | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## C1. Scalability
Requirement |  |  |  |  | OpenSource Tool(s) Evaluated | Criteria | [13 empty] | Total Estimated Gap Effort [PM] | Potential Developer Group | Total Requirement Effort for 2011 [PM] | Total Requirement Effort [PM]
Category | Requirement Name | Req. Id | Priority | Detailed capability |  | Functionality |  | Customizability |  | Extensibility |  | Scalability |  | Usability |  | Interoperability |  | Documentation
[6 empty] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM]
C. Core Platform Features for Enterprise Use 1. Support for large models, including lazy loading, partial collection handling | Support for models containing 500 000+ model objects | 1.1 a) |  | General requirement/theme; needs to be considered as criterion and individually taken into account in effort estimates for each specific requirement; cannot be globally analyzed and estimated in terms of effort | any |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| Tools built on MP scale to large models (e.g., diagram editors) | 1.1 b) |  | General requirement/theme; needs to be considered as criterion and individually taken into account in effort estimates for each specific requirement; cannot be globally analyzed and estimated in terms of effort | any |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| 300 000 model objects in 7000 resources | Use Case |  | General requirement/theme; needs to be considered as criterion and individually taken into account in effort estimates for each specific requirement; cannot be globally analyzed and estimated in terms of effort | any |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| 60 000 changes recordable in versioning system | Use Case |  | General requirement/theme; needs to be considered as criterion and individually taken into account in effort estimates for each specific requirement; cannot be globally analyzed and estimated in terms of effort | any |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| 3000 sequence diagrams, 450 MB file size | Use Case |  | General requirement/theme; needs to be considered as criterion and individually taken into account in effort estimates for each specific requirement; cannot be globally analyzed and estimated in terms of effort | any |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| 200 000 model objects and 900 000 references | Use Case |  | General requirement/theme; needs to be considered as criterion and individually taken into account in effort estimates for each specific requirement; cannot be globally analyzed and estimated in terms of effort | any |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0

## C2. Offline Support
Requirement |  |  |  |  | OpenSource Tool(s) Evaluated | Criteria | [13 empty] | Total Estimated Gap Effort [PM] | Potential Developer Group | Total Requirement Effort for 2011 [PM] | Total Requirement Effort [PM]
Category | Requirement Name | Req. Id | Priority | Detailed capability |  | Functionality |  | Customizability |  | Extensibility |  | Scalability |  | Usability |  | Interoperability |  | Documentation
[6 empty] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM]
C. Core Platform Features for Enterprise Use 2. Ability to work offline and then merge changes back into a model | Support for extraction of partial view of model from repository and reintegration of updated view | 2.1 |  | Aspects extraction of copy of model from repository which can be used offline and reintegration of changes into repository at some later time covered by "A1. Version Management"; Aspect partial extraction/reintegration of models supported for models from SCM systems; not easily feasible for models in model repositories without risk of violating the model repository's refential integrity. Should be reconsidered at a later point in time based on a concrete use case such as to see if this capability is really necessary and to which extent. No further analysis and effort estimation possible based on currently available information. |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| Tools built on MP must be usable without network connection | 2.2 a) |  | General requirement/theme; needs to be considered as criterion and individually taken into account in effort estimates for each specific requirement; cannot be globally analyzed and estimated in terms of effort | any |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| Extracted partial model view must be usable offline | 2.2 b) |  | Aspects extraction of copy of model from repository which can be used offline and reintegration of changes into repository at some later time covered by "A1. Version Management"; Aspect partial extraction/reintegration of models supported for models from SCM systems; not easily feasible for models in model repositories without risk of violating the model repository's refential integrity. Should be reconsidered at a later point in time based on a concrete use case such as to see if this capability is really necessary and to which extent. No further analysis and effort estimation possible based on currently available information. |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0

## C3. Metamodel Compatibility
Requirement |  |  |  |  | OpenSource Tool(s) Evaluated | Criteria | [13 empty] | Total Estimated Gap Effort [PM] | Potential Developer Group | Total Requirement Effort for 2011 [PM] | Total Requirement Effort [PM]
Category | Requirement Name | Req. Id | Priority | Detailed capability |  | Functionality |  | Customizability |  | Extensibility |  | Scalability |  | Usability |  | Interoperability |  | Documentation
[6 empty] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM]
C. Core Platform Features for Enterprise Use 3. Support for modeling standards and open formats. Lowest denominator is the EObject (Ecore) | All MP services must support any metamodel implementation based on EObject/Ecore | 3.1 |  | General requirement/theme; needs to be considered as criterion and individually taken into account in effort estimates for each specific requirement; cannot be globally analyzed and estimated in terms of effort | any |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0

## C4. Project Lifecycle Support
Requirement |  |  |  |  | OpenSource Tool(s) Evaluated | Criteria |  |  |  | Total Estimated Gap Effort [PM] | Potential Developer Group | Total Requirement Effort for 2011 [PM] | Total Requirement Effort [PM]
Category | Requirement Name | Req. Id | Priority | Detailed capability |  | Functionality |  | Documentation
[6 empty] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM]
C. Core Platform Features for Enterprise Use 4. End-to-End project support from business architecture to code and testing | Support for different types of models during different steps of the software development lifecycle | 4.1 a) |  | Covered by "A6. Migration / Support for different versions of a metamodel in the same environment (6 c))" |  |  | 0 |  | 0 | 0 |  | 0 | 0
| Traceability/impact analysis across different types of models | 4.1 b) |  | Covered by "A5. Traceability" |  |  | 0 |  | 0 | 0 |  | 0 | 0

## D1. Standards Support
Requirement | [5 empty] | OpenSource Tool(s) Evaluated | Criteria | [13 empty] | Total Estimated Gap Effort [PM] | Potential Developer Group | Requirement Effort for 1.0M1 [PM] | Requirement Effort for 1.0M2 [PM] | Requirement Effort for 1.0M3 [PM] | Requirement Effort for 1.0 [PM] | P1 .. P3 Requirement Effort [PM] | P4 .. P5 Requirement Effort [PM] | Total Requirement Effort for 2011 [PM] | Total Requirement Effort [PM]
Category | Requirement Name | Req. Id | Priority | Target Milestone | Detailed capability |  | Functionality |  | Customizability |  | Extensibility |  | Scalability |  | Usability |  | Interoperability |  | Documentation
[7 empty] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM]
D. Flexible Content Support 1. General purpose models based on industry standards like UML, BPMN and SysML | Out of the box support of industry standards UML, BPMN and SysML | 1.1 a) |  |  | Only BPMN support will be detailed here; see requirements E-Auth-1, E-Auth-3, etc. for UML and UML profile support
Alternative 1: UML profile for BPMN
|  |  | 10 |  | Support for the BPMN profile (currently an OMG RFI) | Papyrus UML2 | We assume that the BPMN profile has roughly the same size as the SysML profile | 2 | [11 empty] | 2 | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
|  |  | 20 |  | Integration with existing open source BPMN process engine (e.g., jBPM at JBoss or Activiti) |  | Not supported | 4 | [12 empty] | 4
Alternative 2: BPMN tools for native BPMN DSL
|  |  | 20 |  | EMF implementation of BPMN metamodel | BPMN GMF, Graphiti EMF Validation | Partially supported; a first version of EMF implementation of BPMN metamodel available, but still a lot of outstanding work and no official release yet | 6 | [12 empty] | 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31
|  |  | 20 |  | Model repository support, in particular CDO |  | Not supported; implementation of this capability can benefit from results of "Support for the full UML 2 standard" which requires the same capability | 1 | [12 empty] | 1
|  |  | 20 |  | BPMN design tooling including graphical editors and process pattern validation constraints |  | Not supported | 24 | [12 empty] | 24
|  |  | 30 |  | Integration with existing open source BPMN process engine (e.g., jBPM at JBoss or Activiti) |  | Effort same as in "Alternative 1: UML profile for BPMN", see above | 0 | [12 empty] | 0
| Support for the full UML 2 standard | E-Auth-1 | 1 | 1.0M1 | UML2 metamodel support | Papyrus UML 2 EMF Core Sphinx CDO MXF | Partially supported; currently at version 2.2 of specification needs to be updated to 2.4 | 2 | [12 empty] | 2 | Zeligsoft, Kenn Hussey | 2 | 4 | 0 | 0 | 6 | 0 | 6 | 77
|  |  | 1 | 1.0M2 | Model repository support, in particular CDO |  | Not supported; a CDO-compatible Ecore implementation mùst be made available and UML2 metamodel implementation must be based on it; performance and memory consumption impacts when using CDO compatible UML2 metamodel implementation with file-based UML2 models need to be investigated and eliminated or limited to an acceptable level | 2 | [10 empty] | Update of UML2 and Papyrus user and developer documentation wrt model repository support | 1 | 3 | Zeligsoft, itemis, Eike Stepper, Kenn Hussey
|  |  | 10 |  | Integration of Papyrus with modeling IDE services provided by Sphinx (in particular persistence, scoping, model management, indexing, workspace management, editor management and navigation) |  | Currently Papyrus, in particular the Papyrus Backbone, and Sphinx are partially overlapping; a detailed Papyrus/Sphinx gap analysis followed by a refactoring/migration of overlapping parts in Papyrus/Sphinx need to be done | 6 | [10 empty] | Update of user and developer documentation wrt changes resulting from Papyrus/Sphinx integration | 2 | 8
|  |  | 10 |  | UML model authoring (deployment, object, package, use case, activity, state machine, communication, sequence and interaction overview diagrams) |  | Partially supported; the diagrams are supported, however currently they reveal too much of the underlying UML metamodel which affects the user experience and productivity. Some of the usablity can be solved by customizing Papyrus while others such as show inherited parts in a structure diagram require further implementation work.` | 15 | [10 empty] | The end-user documentation is minimal and needs more examples and tutorials | 6 | 21
|  |  | 20 |  | Support of a basic virtual machine for UML structure and behaviour |  | [MXF] Not supported | 18 | [12 empty] | 18
|  |  | 20 |  | Support in UML2 tooling for execution and animation |  | [Papyrus] Not supported | 12 | [12 empty] | 12
|  |  | 20 |  | Support for showing differences in UML diagrams |  | [Papyrus] Not supported; | 12 | [12 empty] | 12
|  |  | 1 | 1.0M2 | Compare and merge support for UML including the ability to see changes to stereotypes applied to an element |  | [EMF Compare] Not supported | 1 | [12 empty] | 1 | Obeo
| Support for the UML 2 profile mechanism | E-Auth-2 | 1 |  | Metamodel support | Papyrus UML2 | Partially supported; currently at version 2.2 of specification needs to be updated to 2.4; effort estimate included in "Support for the full UML 2 standard" E-Auth-1 / "UML2 metamodel support", see above | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | Supported | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
|  |  | 1 |  | Static profile definition |  | Supported | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | Supported | 0 | 0
|  |  | 1 |  | Dynamic profile definition |  | Supported | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | Supported | 0 | 0
|  |  | 10 |  | Support for persisting profile application independent of model |  | Not supported | 4 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | Supported | 0 | 4
|  |  | 1 |  | Support customizing view of stereotyped elements |  | Supported | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | Supported | 0 | 0
|  |  | 1 |  | Support customizing icons of stereotyped elements |  | Supported | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | Supported | 0 | 0 | [7 empty] | 0 | 0
|  |  | 1 |  | Support customizing properties view of stereotyped elements |  | Supported | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | Supported | 0 | 0
| OCL language support | E-Auth-3 | 10 |  | Full syntax and semantics support | OCL Papyrus | Supported | 0 | N/A | 0 | Supported | 0 | N/A | 0 | N/A | 0 | N/A | 0 | Supported | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
|  |  | 10 |  | Standard library support |  | Partially supported; MDT OCL CompleteEditor works well with Ecore metamodels but requires support for UML metamodels (Bug 315719) | 3 | N/A | 0 | N/A | 0 | N/A | 0 | Partially supported; the edtior provides little guidance in constructing a correct OCL document and the error markers are cryptic | 3 | N/A | 0 | Not supported; did not find any documentation about the CompleteEditor other than a mention in an example | 1 | 7
|  |  | 10 |  | Support for authoring OCL constraint(s) |  | Partially supported; supported in OCL intepreter and at the code level but it doesn't appear possible to evaluate an OCL document | 4 | N/A | 0 | N/A | 0 | Not supported; since the interpreter does not support evaluating complete documents it is hard to apply many constraints at once | 0 | Not supported; since the interpreter does not support evaluating complete documents it is hard to apply many constraints at once | 0 | N/A | 0 | Not supported; there is very little documentation on this feature, and what is there is not geared towards an end-user | 0 | 4
|  |  | 10 |  | Support for evaluating OCL constraint(s) |  | Supported; it is possible to turn on tracing to see the evaluation of OCL constraints but there is no interactive debugger | 0 | N/A | 0 | N/A | 0 | N/A | 0 | Supported | 0 | N/A | 0 | Supported | 0 | 0
[5 empty] | Support for debugging OCL constraints(s) |  | Not supported | 6 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6
| Support for the OMG standard MARTE profile | E-Auth-6 | 20 |  | Nothing to add | Papyrus UML 2 OCL | Partially supported; some usability improvements | 1 | [7 empty] | 1 |  |  |  | 1 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| Support for the OMG standard SysML profile | E-Auth-7 | 20 |  | Nothing to add | Papyrus UML 2 OCL | Partially supported; some usability improvements | 1 | [7 empty] | 1 |  |  |  | 1 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| Support for the UML Action Language standard | E-Auth-8 | 10 |  | Nothing to add | Xtext(?) JDT(?) | Not supported | 6 | [12 empty] | 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
| Support for the UML RT profile | E-Auth-9 | 10 |  | UML RT profile | Papyrus UML 2 OCL | Not supported | 6 | [12 empty] | 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
|  |  | 10 |  | UML RT code generator |  | Not supported | 12 | [12 empty] | 12
|  |  | 10 |  | UML RT model animation |  | Not supported; effort estimate assumes support for model simulation in the modeling platform | 6 | [12 empty] | 6
|  |  | 10 |  | UML RT model debugging |  | Not supported; effort estimate assumes support for model level debugging in the modeling platform | 6 | [12 empty] | 6
| Rhapsody UML profile | E-Auth-10 | 30 |  | Rhapsody profile | Papyrus UML 2 OCL | Not supported | 6 | [12 empty] | 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
|  |  | 30 |  | Rhapsody code generator |  | Not supported | 12 | [12 empty] | 12
|  |  | 30 |  | Rhapsody model animation |  | Not supported; effort estimate assumes support for model simulation in the modeling platform | 6 | [12 empty] | 6
|  |  | 30 |  | Rhapsody model debugging |  | Not supported; effort estimate assumes support for model level debugging in the modeling platform | 6 | [12 empty] | 6
| Capacity to extend support to any other modeling standard | 1.1 b) |  |  | General requirement/theme, cannot be analyzed as an individual item | any | Supported | 0 | [12 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on F33: Toby McClean: This should allow the user to author more than one constraint in a single document. The constraints may apply to different metamodel elements.
Note on F34: Toby McClean: The user should be able chose the constraint(s) and model elements to evaluate against.
Note on F35: Toby McClean: Provide the ability to step through the evaluation of a OCL constraint.

## D2. DSL Compatibility
Requirement |  |  |  |  | OpenSource Tool(s) Evaluated | Criteria | [13 empty] | Total Estimated Gap Effort [PM] | Potential Developer Group | Total Requirement Effort for 2011 [PM] | Total Requirement Effort [PM]
Category | Requirement Name | Req. Id | Priority | Detailed capability |  | Functionality |  | Customizability |  | Extensibility |  | Scalability |  | Usability |  | Interoperability |  | Documentation
[6 empty] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM]
D. Flexible Content Support 2. Domain Specific Models | All MP services must be applicable to user-defined domain specific modeling languages | 2.1 |  | General requirement/theme; needs to be considered as criterion and individually taken into account in effort estimates for each specific requirement; cannot be globally analyzed and estimated in terms of effort | any |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0
| Support for definition DSLs, handling of DSL instances, validation of DSL instances against corresponding DSL definition | 2.2 |  | General requirement/theme; needs to be considered as criterion and individually taken into account in effort estimates for each specific requirement; cannot be globally analyzed and estimated in terms of effort | any |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 | 0

## D3. M2M-ATL
Ericsson Requirement |  |  |  |  | OpenSource Tool(s) Evaluated | Criteria |  |  |  | Total Estimated Gap Effort [PM] | Potential Developer Group | Total Requirement Effort for 2011 [PM] | Total Requirement Effort [PM]
Category | Requirement Name | Req. Id | Priority | Detailed capability |  | Functionality |  | Documentation
[6 empty] | Discussion | Est. Effort[PM] | Discussion | Est. Effort[PM]
D. Flexible Content Support 3. M2M Transformations | Support for creation of new model transformation templates, update of existing ones, and testing for validity | 3.1 | 10 | Creation of transformation utilities | ATL Sphinx EFacet | Not supported | 1 |  |  | 1 |  | 0 | 15
|  |  | 30 | Allow for the use of name maps |  | Not supported | 1 |  |  | 1
|  |  | 20 | Creation of configuration validation rules |  | Supported | 0 |  |  | 0
|  |  | 10 | Definition of configuration/control properties |  | Not supported | 1 |  |  | 1
|  |  | 10 | Creation of new model transformations and transformation rules |  | Supported; includes wizards and projects to guide the creation of new transformations | 0 |  |  | 0
|  |  | 20 | Extend/customize existing transformation |  | Partially supported; using superimposition you can mask/override an existing rule, however, it doesn't appear possible to extend an existing rule | 2 |  |  | 2
|  |  | 30 | Control whether a transformation can be extended |  | Not supported | 0 |  |  | 0
|  |  | 10 | Debugging - breakpoint support |  | Partially supported; only supported on expressions and not on matching part of a transformation | 2 |  |  | 2
|  |  | 10 | Debugging - inspecting context |  | Supported | 0 |  |  | 0
|  |  | 10 | Debugging - inspecting stack trace |  | Supported; there could be some usability improvements as to the labels presented to the user | 0 |  |  | 0
|  |  | 10 | Debugging - stepping through transformation |  | Supported | 0 |  |  | 0
|  |  | 20 | Debugging - conditional breakpoint |  | Not supported | 3 |  |  | 3
|  |  | 20 | Debugging - expression evaluations |  | Partially supported; there is no view specific to expressions that can be "watched" | 5 |  |  | 5
| Ability to select and apply appropriate model transformation template to one or several models | 3.2 a) | 10 | Define a specific configuration of a transformation |  | Supported | 0 | Not supported | 1 | 1 |  | 0 | 9
|  |  | 30 | Define a hierarchy of configurations |  | Not supported | 3 |  |  | 3
|  |  | 30 | Define a name map |  | Not supported | 0 |  |  | 0
|  |  | 10 | Editor to define a specific configuration of a transformation |  | Not supported | 1 |  |  | 1
|  |  | 10 | Transformation execution provides feedback to user, i.e., progress bar |  | Not supported; using the standard Eclipse progress monitor | 1 |  |  | 1
|  |  | 20 | Applying an extended tranformation includes the extensions |  | Not supported; would be part of support for "extend/customize existing transformation" | 0 |  |  | 0
|  |  | 10 | Execution from within IDE |  | Partially supported; needs integration with Sphinx service for running transformation from centrally managed models that are already loaded | 3 |  |  | 3 | Obeo Geensys
|  |  | 10 | Execution from ANT script |  | Supported | 0 |  |  | 0
|  |  | 10 | Execution from command line |  | Supported | 0 |  |  | 0
|  |  | 10 | Execution through Java API |  | Supported | 0 |  |  | 0
| Capability to obtain transformation result and related information (e.g., error log) | 3.2 b) | 10 | Obtain target model(s) |  | Supported; needs integration with Sphinx service for making target models centrally available and sharing them across different views and editors in the IDE without having to load them separately each time | 1 |  |  | 1 |  | 0 | 2
|  |  | 20 | Obtain transformation trace |  | Supported | 0 |  |  | 0
|  |  | 20 | Integration with diff/merge |  | Not supported | 1 |  |  | 1
| Support for potentially required annotation of source model; availability of suitable annotation capabilities in model authoring tools | 3.2 c) | 20 | Support for annotating/extending source model |  | Not supported; should be realized in a standardized way, e.g., in the context of the proposed EFacet project | 1 |  |  | 1 |  | 0 | 8
|  |  | 20 | User interface for adding/removing/editing source model annotations/extensions |  | Not supported; should be realized in a standardized way, e.g., in the context of the proposed EFacet project | 1 |  |  | 1
|  |  | 20 | Capability to access and process information from source model annotations/extensions with transformation language |  | Not supported | 6 |  |  | 6
| Support of semi-automatic transformation enabling users to interactively guide transformation engine as needed | 3.2 d) | 30 | Ability to embed user prompts in transformation templates at locations where choices have to be made |  | Not supported | 2 |  |  | 2 |  | 0 | 4
|  |  | 30 | Set of standard user prompts |  | Not supported | 1 |  |  | 1
|  |  | 30 | Ability to use user-defined user prompts implemented in Java and provided via an extension point |  | Not supported | 1 |  |  | 1
Note on E4: Toby McClean: Transformation utilities perform routine tasks and facility in the authoring of new transformations. For example, a transformation utlity could check the permissions on the source and targets of the transformation.
Note on E5: Toby McClean: The name map specifies alternate names for target files and folders
Note on E6: Toby McClean: A configuration validation rule(s) ensure that the values for configuration/control properties, input models and target models are valid in the context of the given transformation.
Note on E7: Toby McClean: A configuration or control property allows the transformation user to provide additional information to the transformation in order to control its execution and output. There should be no limitations on the richness of these properties, that is they can be complex structures. The specific values provided to the transformation must be avaialble during the execution of the transformation.
Note on E8: Toby McClean: The definition of the transformation and the rules that compose it should provide the author with some way of controlling the order in which things execute.
Note on E9: Toby McClean: Authoer can add new rules and properties to an existing transformation. Also the ability to replace parts of the transformation.
Note on E10: Toby McClean: This is a flag the user can set to indicate whether the transformation can be extended or not. It is similar to final on a class in Java.
Note on E11: Toby McClean: The ability to set break points in the transformatino that pauses the execution of the tranformation when it reaches that point.
Note on E12: Toby McClean: This allows the transformation other to see the currently values of model elements and properties
Note on E13: Toby McClean: This allows the author to see the current execution stack of the transformation that is executing when it is stopped at a breakpoint.
Note on E14: Toby McClean: Provided functionality like JDT to step through the statements in the transformation.
Note on E18: Toby McClean: A specific configuration of a transformation refers to the ability to define and store values for configuration/control properites, the input model(s)/model element(s) and the target of the transformation.
Note on E19: Toby McClean: A hierarchy of configurations allows the transformation user to define some base configurations that are reused/composed/specialized to create the configurations that are actually used in the execution of a transformation
Note on E20: Toby McClean: The name map specifies alternate names for target files and folders
Note on E21: Toby McClean: In order to make the user experience acceptable a user must be given an editor that is aware of the configuration/control properties, number and type of input model(s) or model element(s) and the number and type of output model(s)
Note on E22: Toby McClean: This for example can be a progess bar that lets the user know what it is currently doing
Note on E23: Toby McClean: When the user applies a transformation like generate C++ that the transformation takes into account the extensions that have been applied to it. That way a user does not have to know the structure of the transformation extensions.
Note on E24: Stephan Eberle: Includes things like actions for invoking configured transformations on model elements or resources in the workspace, threadsafe execution of transformation, operation on already loaded and centrally managed models rather than loading models for each transformation run spearately, transformation progress indication through Eclipse progress view and/or ProgressService dialog, automatic refresh of workspace and view to display model resources/elements resulting from transformation, creation of error markers on input files indicating problems encountered during transformation, label decorator for advertising such problems in tree-based views. As more or less the same functions are needed for integrating plenty of other technologies, I consider that capability should be provided once for all by Sphinx rather than individually by each particular technology.
Note on E29: Toby McClean: The output model(s) or model elements(s) that result from executing the transformation.
Note on E30: Toby McClean: This trace is a map of source element(s) + transformation rule to the target element(s)
Note on E31: Toby McClean: So that if the target model already exists that the user can merge the new target model with the existing one

## D3. M2M-QVTo
Ericsson Requirement |  |  |  |  | OpenSource Tool(s) Evaluated | Criteria |  |  |  | Total Estimated Gap Effort [PM] | Potential Developer Group | Total Requirement Effort for 2011 [PM] | Total Requirement Effort [PM]
Category | Requirement Name | Req. Id | Priority | Detailed capability |  | Functionality |  | Documentation
[6 empty] | Discussion | Est. Effort[PM] | Discussion | Est. Effort[PM]
D. Flexible Content Support 3. M2M Transformations | Support for creation of new model transformation templates, update of existing ones, and testing for validity | 3.1 | 10 | Creation of transformation utilities | QVTo Sphinx EFacet | Supported; blackbox support and intermediate properties and classes | 0 | Not supported | 1 | 1 |  | 0 | 16
|  |  | 30 | Allow for the use of name maps |  | Not supported | 1 | Not supported | 0 | 1
|  |  | 20 | Creation of configuration validation rules |  | Supported | 0 | Not supported | 0 | 0
|  |  | 10 | Definition of configuration/control properties |  | Supported | 0 | Not supported | 0 | 0
|  |  | 10 | Creation of new model transformations and transformation rules |  | Supported | 0 | Not supported; needs documenation for all QVTo capabilities | 6 | 6
|  |  | 20 | Extend/customize existing transformation |  | Supported | 0 | Not supported | 0 | 0
|  |  | 30 | Control whether a transformation can be extended |  | N/A; the language itself doesn’t support (i.e. the standard) | 0 | Not supported | 0 | 0
|  |  | 10 | Debugging - breakpoint support |  | Supported | 0 | Not supported | 0 | 0
|  |  | 10 | Debugging - inspecting context |  | Supported | 0 | Not supported | 0 | 0
|  |  | 10 | Debugging - inspecting stack trace |  | Supported | 0 | Not supported | 0 | 0
|  |  | 10 | Debugging - stepping through transformation |  | Supported | 0 | Not supported | 0 | 0
|  |  | 20 | Debugging - conditional breakpoint |  | Not supported | 3 | Not supported | 0 | 3
|  |  | 20 | Debugging - expression evaluations |  | Not supported | 5 | Not supported | 0 | 5
| Ability to select and apply appropriate model transformation template to one or several models | 3.2 a) | 10 | Define a specific configuration of a transformation |  | Supported; possible through launch configurations | 0 | Not supported | 0 | 0 |  | 0 | 7
|  |  | 30 | Define a hierarchy of configurations |  | Not supported | 3 | Not supported | 0 | 3
|  |  | 30 | Define a name map |  | Not supported | 0 | Not supported | 0 | 0
|  |  | 10 | Editor to define a specific configuration of a transformation |  | Supported; possible through launch configurations | 0 | Not supported | 0 | 0
|  |  | 10 | Transformation execution provides feedback to user, i.e., progress bar |  | Supported; through logging facilities | 0 | Not supported | 0 | 0
|  |  | 20 | Applying an extended tranformation includes the extensions |  | Supported | 0 | Not supported | 0 | 0
|  |  | 10 | Execution from within IDE |  | Partially supported; needs integration with Sphinx service for running transformation from centrally managed models that are already loaded | 3 | Not supported | 0 | 3
|  |  | 10 | Execution from ANT script |  | Not supported | 1 | Not supported | 0 | 1
|  |  | 10 | Execution from command line |  | Not supported; included in the ANT script estimate | 0 | Not supported | 0 | 0
|  |  | 10 | Execution through Java API |  | Supported | 0 | Not supported | 0 | 0
| Capability to obtain transformation result and related information (e.g., error log) | 3.2 b) | 10 | Obtain target model(s) |  | Supported; needs integration with Sphinx service for making target models centrally available and sharing them across different views and editors in the IDE without having to load them separately each time | 1 |  |  | 1 |  | 0 | 2
|  |  | 20 | Obtain transformation trace |  | Supported | 0 | Not supported | 0 | 0
|  |  | 20 | Integration with diff/merge |  | Not supported | 1 | Not supported | 0 | 1
| Support for potentially required annotation of source model; availability of suitable annotation capabilities in model authoring tools | 3.2 c) | 20 | Support for annotating/extending source model |  | Not supported; should be realized in a standardized way, e.g., in the context of the proposed EFacet project | 1 |  |  | 1 |  | 0 | 8
|  |  | 20 | User interface for adding/removing/editing source model annotations/extensions |  | Not supported; should be realized in a standardized way, e.g., in the context of the proposed EFacet project | 1 |  |  | 1
|  |  | 20 | Capability to access and process information from source model annotations/extensions with transformation language |  | Not supported | 6 | Not supported | 0 | 6
| Support of semi-automatic transformation enabling users to interactively guide transformation engine as needed | 3.2 d) | 30 | Ability to embed user prompts in transformation templates at locations where choices have to be made |  | Not supported | 2 | Not supported | 0 | 2 |  | 0 | 4
|  |  | 30 | Set of standard user prompts |  | Not supported | 1 | Not supported | 0 | 1
|  |  | 30 | Ability to use user-defined user prompts implemented in Java and provided via an extension point |  | Not supported | 1 | Not supported | 0 | 1
Note on E4: Toby McClean: Transformation utilities perform routine tasks and facility in the authoring of new transformations. For example, a transformation utlity could check the permissions on the source and targets of the transformation.
Note on E5: Toby McClean: The name map specifies alternate names for target files and folders
Note on E6: Toby McClean: A configuration validation rule(s) ensure that the values for configuration/control properties, input models and target models are valid in the context of the given transformation.
Note on E7: Toby McClean: A configuration or control property allows the transformation user to provide additional information to the transformation in order to control its execution and output. There should be no limitations on the richness of these properties, that is they can be complex structures. The specific values provided to the transformation must be avaialble during the execution of the transformation.
Note on E8: Toby McClean: The definition of the transformation and the rules that compose it should provide the author with some way of controlling the order in which things execute.
Note on E9: Toby McClean: Authoer can add new rules and properties to an existing transformation. Also the ability to replace parts of the transformation.
Note on E10: Toby McClean: This is a flag the user can set to indicate whether the transformation can be extended or not. It is similar to final on a class in Java.
Note on E11: Toby McClean: The ability to set break points in the transformatino that pauses the execution of the tranformation when it reaches that point.
Note on E12: Toby McClean: This allows the transformation other to see the currently values of model elements and properties
Note on E13: Toby McClean: This allows the author to see the current execution stack of the transformation that is executing when it is stopped at a breakpoint.
Note on E14: Toby McClean: Provided functionality like JDT to step through the statements in the transformation.
Note on E18: Toby McClean: A specific configuration of a transformation refers to the ability to define and store values for configuration/control properites, the input model(s)/model element(s) and the target of the transformation.
Note on E19: Toby McClean: A hierarchy of configurations allows the transformation user to define some base configurations that are reused/composed/specialized to create the configurations that are actually used in the execution of a transformation
Note on E20: Toby McClean: The name map specifies alternate names for target files and folders
Note on E21: Toby McClean: In order to make the user experience acceptable a user must be given an editor that is aware of the configuration/control properties, number and type of input model(s) or model element(s) and the number and type of output model(s)
Note on E22: Toby McClean: This for example can be a progess bar that lets the user know what it is currently doing
Note on E23: Toby McClean: When the user applies a transformation like generate C++ that the transformation takes into account the extensions that have been applied to it. That way a user does not have to know the structure of the transformation extensions.
Note on E24: Stephan Eberle: Includes things like actions for invoking configured transformations on model elements or resources in the workspace, threadsafe execution of transformation, operation on already loaded and centrally managed models rather than loading models for each transformation run spearately, transformation progress indication through Eclipse progress view and/or ProgressService dialog, automatic refresh of workspace and view to display model resources/elements resulting from transformation, creation of error markers on input files indicating problems encountered during transformation, label decorator for advertising such problems in tree-based views. As more or less the same functions are needed for integrating plenty of other technologies, I consider that capability should be provided once for all by Sphinx rather than individually by each particular technology.
Note on E29: Toby McClean: The output model(s) or model elements(s) that result from executing the transformation.
Note on E30: Toby McClean: This trace is a map of source element(s) + transformation rule to the target element(s)
Note on E31: Toby McClean: So that if the target model already exists that the user can merge the new target model with the existing one

## D3. M2M-Xtend
Ericsson Requirement |  |  |  |  | OpenSource Tool(s) Evaluated | Criteria |  |  |  | Total Estimated Gap Effort [PM] | Potential Developer Group | Total Requirement Effort for 2011 [PM] | Total Requirement Effort [PM]
Category | Requirement Name | Req. Id | Priority | Detailed capability |  | Functionality |  | Documentation
[6 empty] | Discussion | Est. Effort[PM] | Discussion | Est. Effort[PM]
D. Flexible Content Support 3. M2M Transformations | Support for creation of new model transformation templates, update of existing ones, and testing for validity | 3.1 | 10 | Creation of transformation utilities | Xtend/MWE Sphinx EFacet | Supported; basic functions exists | 0 |  |  | 0 |  | 0 | 10
|  |  | 30 | Allow for the use of name maps |  | Not supported; is supported but not yet implemented as a feature. Estimates are for a simple implementation as feature. | 1 |  |  | 1 | itemis
|  |  | 20 | Creation of configuration validation rules |  | Supported | 0 |  |  | 0
|  |  | 10 | Definition of configuration/control properties |  | Supported | 0 |  |  | 0
|  |  | 10 | Creation of new model transformations and transformation rules |  | Partially supported; will not support graphical transformations but needs improvements: dengling reference detection, easier standard mappings | 1 |  |  | 1 | itemis
|  |  | 20 | Extend/customize existing transformation |  | Supported | 0 |  |  | 0
|  |  | 30 | Control whether a transformation can be extended |  | Supported | 0 |  |  | 0
|  |  | 10 | Debugging - breakpoint support |  | Supported | 0 |  |  | 0
|  |  | 10 | Debugging - inspecting context |  | Supported | 0 |  |  | 0
|  |  | 10 | Debugging - inspecting stack trace |  | Supported | 0 |  |  | 0
|  |  | 10 | Debugging - stepping through transformation |  | Supported | 0 |  |  | 0
|  |  | 20 | Debugging - conditinal breakpoint |  | Not supported; but certainly needed. Large refactoring of debugger neccessary for improvement. | 3 |  |  | 3 | itemis
|  |  | 20 | Debugging - expression evaluations |  | Not supported; but certainly needed. Large refactoring of debugger neccessary for improvement. | 5 |  |  | 5
| Ability to select and apply appropriate model transformation template to one or several models | 3.2 a) | 10 | Define a specific configuration of a transformation |  | Supported | 0 |  |  | 0 |  | 0 | 9
|  |  | 30 | Define a hierarchy of configurations |  | Not supported; Does not fit well into the Xtend context. Needs new concepts and implementation | 3 |  |  | 3 | itemis
|  |  | 30 | Define a name map |  | Partially supported; UI Support needed | 1 |  |  | 1 | itemis
|  |  | 10 | Editor to define a specific configuration of a transformation |  | Not supported | 1 |  |  | 1 | itemis
|  |  | 10 | Transformation execution provides feedback to user, i.e., progress bar |  | Supported; in form of console logging, improvement needed | 1 |  |  | 1 | itemis
|  |  | 20 | Applying an extended tranformation includes the extensions |  | Supported; through extend/customize existing transformation | 0 |  |  | 0
|  |  | 10 | Execution from within IDE |  | Partially supported; Creation of launch configurations must be simplified or made avoidable, execution without need for separate workspace must be possible; needs integration with Sphinx service for running transformation from centrally managed models that are already loaded | 3 |  |  | 3 | itemis Geensys
|  |  | 10 | Execution from ANT script |  | Supported | 0 |  |  | 0
|  |  | 10 | Execution from command line |  | Supported | 0 |  |  | 0
|  |  | 10 | Execution through Java API |  | Supported | 0 |  |  | 0
| Capability to obtain transformation result and related information (e.g., error log) | 3.2 b) | 10 | Obtain target model(s) |  | Supported; needs integration with Sphinx service for making target models centrally available and sharing them across different views and editors in the IDE without having to load them separately each time | 1 |  |  | 1 |  | 0 | 2
|  |  | 20 | Obtain transformation trace |  | Supported; basic functionality exists but improvements needed: automatic trace model but no UI support | 1 |  |  | 1 | itemis
|  |  | 20 | Integration with diff/merge |  | Supported | 0 |  |  | 0
| Support for potentially required annotation of source model; availability of suitable annotation capabilities in model authoring tools | 3.2 c) | 20 | Support for annotating/extending source model |  | Not supported; should be realized in a standardized way, e.g., in the context of the proposed EFacet project | 1 |  | 1 | 2 |  | 0 | 10
|  |  | 20 | User interface for adding/removing/editing source model annotations/extensions |  | Not supported; should be realized in a standardized way, e.g., in the context of the proposed EFacet project | 1 |  | 1 | 2
|  |  | 20 | Capability to access and process information from source model annotations/extensions with transformation language |  | Not supported | 6 |  |  | 6
| Support of semi-automatic transformation enabling users to interactively guide transformation engine as needed | 3.2 d) | 30 | Ability to embed user prompts in transformation templates at locations where choices have to be made |  | Not supported; Needs UI support as well as feature itself | 2 |  |  | 2 |  | 0 | 4
|  |  | 30 | Set of standard user prompts |  | Not supported; Needs UI support as well as feature itself | 1 |  |  | 1
|  |  | 30 | Ability to use user-defined user prompts implemented in Java and provided via an extension point |  | Not supported; Needs UI support as well as feature itself | 1 |  |  | 1
Note on E4: Toby McClean: Transformation utilities perform routine tasks and facility in the authoring of new transformations. For example, a transformation utlity could check the permissions on the source and targets of the transformation.
Note on E5: Toby McClean: The name map specifies alternate names for target files and folders
Note on E6: Toby McClean: A configuration validation rule(s) ensure that the values for configuration/control properties, input models and target models are valid in the context of the given transformation.
Note on E7: Toby McClean: A configuration or control property allows the transformation user to provide additional information to the transformation in order to control its execution and output. There should be no limitations on the richness of these properties, that is they can be complex structures. The specific values provided to the transformation must be avaialble during the execution of the transformation.
Note on E8: Toby McClean: The definition of the transformation and the rules that compose it should provide the author with some way of controlling the order in which things execute.
Note on E9: Toby McClean: Authoer can add new rules and properties to an existing transformation. Also the ability to replace parts of the transformation.
Note on E10: Toby McClean: This is a flag the user can set to indicate whether the transformation can be extended or not. It is similar to final on a class in Java.
Note on E11: Toby McClean: The ability to set break points in the transformatino that pauses the execution of the tranformation when it reaches that point.
Note on E12: Toby McClean: This allows the transformation other to see the currently values of model elements and properties
Note on E13: Toby McClean: This allows the author to see the current execution stack of the transformation that is executing when it is stopped at a breakpoint.
Note on E14: Toby McClean: Provided functionality like JDT to step through the statements in the transformation.
Note on E18: Toby McClean: A specific configuration of a transformation refers to the ability to define and store values for configuration/control properites, the input model(s)/model element(s) and the target of the transformation.
Note on E19: Toby McClean: A hierarchy of configurations allows the transformation user to define some base configurations that are reused/composed/specialized to create the configurations that are actually used in the execution of a transformation
Note on E20: Toby McClean: The name map specifies alternate names for target files and folders
Note on E21: Toby McClean: In order to make the user experience acceptable a user must be given an editor that is aware of the configuration/control properties, number and type of input model(s) or model element(s) and the number and type of output model(s)
Note on E22: Toby McClean: This for example can be a progess bar that lets the user know what it is currently doing
Note on E23: Toby McClean: When the user applies a transformation like generate C++ that the transformation takes into account the extensions that have been applied to it. That way a user does not have to know the structure of the transformation extensions.
Note on E24: Stephan Eberle: Includes things like actions for invoking configured transformations on model elements or resources in the workspace, threadsafe execution of transformation, operation on already loaded and centrally managed models rather than loading models for each transformation run spearately, transformation progress indication through Eclipse progress view and/or ProgressService dialog, automatic refresh of workspace and view to display model resources/elements resulting from transformation, creation of error markers on input files indicating problems encountered during transformation, label decorator for advertising such problems in tree-based views. As more or less the same functions are needed for integrating plenty of other technologies, I consider that capability should be provided once for all by Sphinx rather than individually by each particular technology.
Note on E29: Toby McClean: The output model(s) or model elements(s) that result from executing the transformation.
Note on E30: Toby McClean: This trace is a map of source element(s) + transformation rule to the target element(s)
Note on E31: Toby McClean: So that if the target model already exists that the user can merge the new target model with the existing one

## D4. M2T-Acceleo
Ericsson Requirement |  |  |  |  | OpenSource Tool(s) Evaluated | Criteria |  |  |  | Total Estimated Gap Effort [PM] | Potential Developer Group | Total Requirement Effort for 2011 [PM] | Total Requirement Effort [PM]
Category | Requirement Name | Req. Id | Priority | Detailed capability |  | Functionality |  | Documentation
[6 empty] | Discussion | Est. Effort[PM] | Discussion | Est. Effort [PM]
D. Flexible Content Support 4. Model to Text (M2T) Transformations | Support for generation of source code, documentation and test cases from a model | 4.1 + E-Doc-1 | 10 | Creation of transformation utilities | Acceleo Sphinx | Supported | 0 | Partially supported; documentation for wizards is provided but outside of that there is no documentation for this capability | 1 | 1 |  | 0 | 12
|  |  | 30 | Allow for the use of name maps |  | Not supported | 1 | Not supported | 0 | 1
|  |  | 20 | Creation of configuration validation rules |  | Supported | 0 | Not supported | 0 | 0
|  |  | 10 | Definition of configuration/control properties |  | Partially supported; possible to specify a properties file that can configure/control the template however it does not appear easy to use as it uses ResourceBundle needs to be much easier to specify specific configurations Could be supported through MWE | 1 | Partially supported; describes the current approach to providing control/configuration properties however it does not give any examples on how to do it | 1 | 2
|  |  | 10 | Creation of new model transformations and transformation rules |  | Supported | 0 | Supported | 0 | 0
|  |  | 20 | Extend/customize existing transformation |  | Supported | 0 | Documentation shows how to override either dynamically or statically but does not describe the execution semantics of overriding or provide sufficient examples. | 1 | 1
|  |  | 30 | Control whether a transformation can be extended |  | Not supported | 1 | Not supported | 0 | 1
|  |  | 10 | Debugging - breakpoint support |  | Supported | 0 | Supported | 0 | 0
|  |  | 10 | Debugging - inspecting context |  | Supported | 0 | Supported | 0 | 0
|  |  | 10 | Debugging - inspecting stack trace |  | Supported | 0 | Supported | 0 | 0
|  |  | 10 | Debugging - stepping through transformation |  | Supported | 0 | Supported | 0 | 0
|  |  | 20 | Debugging - conditional breakpoint |  | Supported; using OCL expressions | 0 | Supported | 0 | 0
|  |  | 20 | Debugging - expression evaluations |  | Not supported | 5 | Not supported | 0 | 5
|  |  | 10 | Compilation |  | Supported; compiles to an OMG MTL engine (both a strict compliance and a more pragmatic compliance) | 0 | Partially supported; documentation is provided for how to control the compilation but it is incomplete for the exact differences between strict and pragmatic modes | 1 | 1
|  |  | 20 | Profiling and Optimization |  | Supported | 0 | Supported | 0 | 0
|  |  | 30 | Refactorings |  | Supported; supports a standard set of refactorings | 0 | Supported; standard set of refactorings are documented | 0 | 0
|  |  | 10 | Generate HTML |  | Supported | 0 | Supported | 0 | 0
|  |  |  | Generate PDF |  | N/A | 0 | N/A | 0 | 0
|  |  |  | Generate Word Document |  | N/A | 0 | N/A | 0 | 0
|  |  |  | Ability to include diagrams in documents |  | N/A | 0 | N/A | 0 | 0
|  |  | 10 | Document templates metamodel aware |  | Supported | 0 | Supported | 0 | 0
|  |  | 10 | Document templates support UML stereotypes |  | Supported | 0 | Supported | 0 | 0
|  |  | 10 | Document templates support generating for a subset of the model |  | Supported | 0 | Supported | 0 | 0
|  |  | 10 | Document templates can be invoked in headless mode |  | Supported | 0 | Supported | 0 | 0
|  |  | 10 | Document templates support SQL like expressions |  | Supported | 0 | Supported | 0 | 0
|  |  | 10 | Document templates support SQL like queries |  | Supported | 0 | Supported | 0 | 0
|  |  | 10 | Document templates support SQL like grouping |  | Supported | 0 | Supported | 0 | 0
|  |  | 10 | Document templates support extensions through Java |  | Supported | 0 | Supported | 0 | 0
| Ability to select and apply appropriate generation template to one or several models | 4.2 (proposed) | 10 | Define a specific configuration of a transformation |  | Supported | 0 | Not supported | 1 | 1 |  | 0 | 8
|  |  | 30 | Define a hierarchy of configurations |  | Not supported | 1 | Not supported | 0 | 1
|  |  | 30 | Define a name map |  | Not supported | 0 | Not supported | 0 | 0
|  |  | 10 | Editor to define a specific configuration of a code generation, i.e., the UI of the Acceleo launch configuration |  | Supported | 0 | Not supported | 0 | 0
|  |  | 10 | Code generation execution provides feedback to user, i.e., progress bar |  | Not supported | 1 | N/A | 0 | 1
|  |  | 20 | Applying an extended tranformation includes the extensions |  | Supported | 0 | Supported | 0 | 0
|  |  | 10 | Execution from within IDE |  | Partially supported; needs integration with Sphinx service for running transformation from centrally managed models that are already loaded | 3 | Supported | 0 | 3 | itemis Geensys
|  |  | 10 | Execution from ANT script |  | Not supported | 1 | Not supported | 1 | 2
|  |  | 10 | Execution from command line |  | Not supported | 0 | Not supported | 0 | 0
|  |  | 10 | Execution through Java API |  | Supported | 0 | Supported | 0 | 0
| Open, modifiable, and extensible code generation specifications | E-CdGen-1 |  | Nothing to add |  | Supported | 0 | Supported | 0 | 0 |  | 0 | 0
| Ability to generate code for different target languages | E-CdGen-2 | 10 | Obtain target model(s) and/or text |  | Supported | 0 | Supported | 0 | 0 |  | 0 | 0
|  |  | 20 | Obtain transformation trace |  | Not supported | 0 | Not supported | 0 | 0
|  |  |  | Integration with diff/merge |  | N/A | 0 | N/A | 0 | 0
| Ability to define incremental and scalable code generators and compilations | E-CdGen-4 |  | Not clear what this requirement exactly means |  | N/A | 0 | N/A | 0 | 0 |  | 0 | 0
| Code generation support for easy debugging of generated code | E-CdGen-6 |  | This is a question of how the code generation templates are designed but not on the technology used for running them. The requirement therefore is deemd as not applicable. |  | N/A | 0 | N/A | 0 | 0 |  | 0 | 0
Note on E4: Toby McClean: Transformation utilities perform routine tasks and facility in the authoring of new transformations. For example, a transformation utlity could check the permissions on the source and targets of the transformation.
Note on E5: Toby McClean: The name map specifies alternate names for target files and folders
Note on E6: Toby McClean: A configuration validation rule(s) ensure that the values for configuration/control properties, input models and target models are valid in the context of the given transformation.
Note on E7: Toby McClean: A configuration or control property allows the transformation user to provide additional information to the transformation in order to control its execution and output. There should be no limitations on the richness of these properties, that is they can be complex structures. The specific values provided to the transformation must be avaialble during the execution of the transformation.
Note on E8: Toby McClean: The definition of the transformation and the rules that compose it should provide the author with some way of controlling the order in which things execute.
Note on E9: Toby McClean: Authoer can add new rules and properties to an existing transformation. Also the ability to replace parts of the transformation.
Note on E10: Toby McClean: This is a flag the user can set to indicate whether the transformation can be extended or not. It is similar to final on a class in Java.
Note on E11: Toby McClean: The ability to set break points in the transformatino that pauses the execution of the tranformation when it reaches that point.
Note on E12: Toby McClean: This allows the transformation other to see the currently values of model elements and properties
Note on E13: Toby McClean: This allows the author to see the current execution stack of the transformation that is executing when it is stopped at a breakpoint.
Note on E14: Toby McClean: Provided functionality like JDT to step through the statements in the transformation.
Note on E33: Toby McClean: A specific configuration of a transformation refers to the ability to define and store values for configuration/control properites, the input model(s)/model element(s) and the target of the transformation.
Note on E34: Toby McClean: A hierarchy of configurations allows the transformation user to define some base configurations that are reused/composed/specialized to create the configurations that are actually used in the execution of a transformation
Note on E35: Toby McClean: The name map specifies alternate names for target files and folders
Note on E36: Toby McClean: In order to make the user experience acceptable a user must be given an editor that is aware of the configuration/control properties, number and type of input model(s) or model element(s) and the number and type of output model(s)
Note on E37: Toby McClean: This for example can be a progess bar that lets the user know what it is currently doing
Note on E38: Toby McClean: When the user applies a transformation like generate C++ that the transformation takes into account the extensions that have been applied to it. That way a user does not have to know the structure of the transformation extensions.
Note on E39: Stephan Eberle: Includes things like actions for invoking configured transformations on model elements or resources in the workspace, threadsafe execution of transformation, operation on already loaded and centrally managed models rather than loading models for each transformation run spearately, transformation progress indication through Eclipse progress view and/or ProgressService dialog, automatic refresh of workspace and view to display model resources/elements resulting from transformation, creation of error markers on input files indicating problems encountered during transformation, label decorator for advertising such problems in tree-based views. As more or less the same functions are needed for integrating plenty of other technologies, I consider that capability should be provided once for all by Sphinx rather than individually by each particular technology.
Note on C44: Toby McClean: I think that this can be collapsed into 4.1
Note on E46: Toby McClean: The output model(s) or model elements(s) that result from executing the transformation.
Note on E47: Toby McClean: This trace is a map of source element(s) + transformation rule to the target element(s)
Note on E48: Toby McClean: So that if the target model already exists that the user can merge the new target model with the existing one
Note on C52: Toby McClean: Not sure that I understand how this one is a M2T requirement. This is actually a requirement on the transformation author.

## D4. M2T-BIRT
Ericsson Requirement | [5 empty] | OpenSource Tool(s) Evaluated | Criteria |  |  |  | Total Estimated Gap Effort [PM] | Potential Developer Group | Requirement Effort for 1.0M1 [PM] | Requirement Effort for 1.0M2 [PM] | Requirement Effort for 1.0M3 [PM] | Requirement Effort for 1.0 [PM] | P1 .. P3 Requirement Effort [PM] | P4 .. P5 Requirement Effort [PM] | Total Requirement Effort for 2011 [PM] | Total Requirement Effort [PM]
Category | Requirement Name | Req. Id | Priority | Target Milestone | Detailed capability |  | Functionality |  | Documentation
[7 empty] | Discussion | Est. Effort[PM] | Discussion | Est. Effort [PM]
D. Flexible Content Support 4. Model to Text (M2T) Transformations | Support for generation of source code, documentation and test cases from a model | 4.1 + E-Doc-1 |  |  | Creation of transformation utilities | BIRT Sphinx | N/A | 0 | N/A | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
[5 empty] | Allow for the use of name maps |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Creation of configuration validation rules |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Definition of configuration/control properties |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Creation of new model transformations and transformation rules |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Extend/customize existing transformation |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Control whether a transformation can be extended |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Debugging - breakpoint support |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Debugging - inspecting context |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Debugging - inspecting stack trace |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Debugging - stepping through transformation |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Debugging - conditinal breakpoint |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Debugging - expression evaluations |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Compilation |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Profiling and Optimization |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Refactorings |  | N/A | 0 | N/A | 0 | 0
|  |  | 10 |  | Generate HTML |  | Supported | 0 | Supported | 0 | 0
|  |  | 10 |  | Generate PDF |  | Supported | 0 | Supported | 0 | 0
|  |  | 10 |  | Generate Word Document |  | Supported | 0 | Supported | 0 | 0
|  |  | 10 |  | Ability to include diagrams in documents |  | Not supported | 6 | Not supported | 0 | 6
|  |  | 10 |  | Document templates metamodel aware |  | Not supported; ODA driver for EMF needed, using Sphinx infrastructure for loading EMF models from files or repositories | 3 | Not supported | 0 | 3
|  |  | 10 |  | Document templates support UML stereotypes |  | Not supported | 1 | Not supported | 0 | 1
|  |  | 10 |  | Document templates support generating for a subset of the model |  | Supported | 0 | Supported | 0 | 0
|  |  | 10 |  | Document templates can be invoked in headless mode |  | Supported | 0 | Supported | 0 | 0
|  |  | 10 |  | Document templates support SQL like expressions |  | Supported | 0 | Supported | 0 | 0
|  |  | 10 |  | Document templates support SQL like queries |  | Supported | 0 | Supported | 0 | 0
|  |  | 10 |  | Document templates support SQL like grouping |  | Supported | 0 | Supported | 0 | 0
|  |  | 10 |  | Document templates support extensions through Java |  | Supported | 0 | Supported | 0 | 0
| Ability to select and apply appropriate generation template to one or several models | 4.2 (proposed) |  |  | Define a specific configuration of a transformation |  | N/A | 0 | N/A | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Define a hierarchy of configurations |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Define a name map |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Editor to define a specific configuration of a transformation |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Code generation execution provides feedback to user, i.e., progress bar |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Applying an extended tranformation includes the extensions |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Execution from within IDE |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Execution from ANT script |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Execution from command line |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Execution through Java API |  | N/A | 0 | N/A | 0 | 0
| Open, modifiable, and extensible code generation specifications | E-CdGen-1 |  |  | Nothing to add |  | N/A | 0 | N/A | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ability to generate code for different target languages | E-CdGen-2 |  |  | Obtain target model(s) and/or text |  | N/A | 0 | N/A | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Obtain transformation trace |  | N/A | 0 | N/A | 0 | 0
[5 empty] | Integration with diff/merge |  | N/A | 0 | N/A | 0 | 0
| Ability to define incremental and scalable code generators and compilations | E-CdGen-4 |  |  | Not clear what this requirement exactly means |  | N/A | 0 | N/A | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code generation support for easy debugging of generated code | E-CdGen-6 |  |  | This is a question of how the code generation templates are designed but not on the technology used for running them. The requirement therefore is deemd as not applicable. |  | N/A | 0 | N/A | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on F4: Toby McClean: Transformation utilities perform routine tasks and facility in the authoring of new transformations. For example, a transformation utlity could check the permissions on the source and targets of the transformation.
Note on F5: Toby McClean: The name map specifies alternate names for target files and folders
Note on F6: Toby McClean: A configuration validation rule(s) ensure that the values for configuration/control properties, input models and target models are valid in the context of the given transformation.
Note on F7: Toby McClean: A configuration or control property allows the transformation user to provide additional information to the transformation in order to control its execution and output. There should be no limitations on the richness of these properties, that is they can be complex structures. The specific values provided to the transformation must be avaialble during the execution of the transformation.
Note on F8: Toby McClean: The definition of the transformation and the rules that compose it should provide the author with some way of controlling the order in which things execute.
Note on F9: Toby McClean: Authoer can add new rules and properties to an existing transformation. Also the ability to replace parts of the transformation.
Note on F10: Toby McClean: This is a flag the user can set to indicate whether the transformation can be extended or not. It is similar to final on a class in Java.
Note on F11: Toby McClean: The ability to set break points in the transformatino that pauses the execution of the tranformation when it reaches that point.
Note on F12: Toby McClean: This allows the transformation other to see the currently values of model elements and properties
Note on F13: Toby McClean: This allows the author to see the current execution stack of the transformation that is executing when it is stopped at a breakpoint.
Note on F14: Toby McClean: Provided functionality like JDT to step through the statements in the transformation.
Note on F33: Toby McClean: A specific configuration of a transformation refers to the ability to define and store values for configuration/control properites, the input model(s)/model element(s) and the target of the transformation.
Note on F34: Toby McClean: A hierarchy of configurations allows the transformation user to define some base configurations that are reused/composed/specialized to create the configurations that are actually used in the execution of a transformation
Note on F35: Toby McClean: The name map specifies alternate names for target files and folders
Note on F36: Toby McClean: In order to make the user experience acceptable a user must be given an editor that is aware of the configuration/control properties, number and type of input model(s) or model element(s) and the number and type of output model(s)
Note on F37: Toby McClean: This for example can be a progess bar that lets the user know what it is currently doing
Note on F38: Toby McClean: When the user applies a transformation like generate C++ that the transformation takes into account the extensions that have been applied to it. That way a user does not have to know the structure of the transformation extensions.
Note on F39: Stephan Eberle: Includes things like actions for invoking configured transformations on model elements or resources in the workspace, threadsafe execution of transformation, operation on already loaded and centrally managed models rather than loading models for each transformation run spearately, transformation progress indication through Eclipse progress view and/or ProgressService dialog, automatic refresh of workspace and view to display model resources/elements resulting from transformation, creation of error markers on input files indicating problems encountered during transformation, label decorator for advertising such problems in tree-based views. As more or less the same functions are needed for integrating plenty of other technologies, I consider that capability should be provided once for all by Sphinx rather than individually by each particular technology.
Note on C44: Toby McClean: I think that this can be collapsed into 4.1
Note on F46: Toby McClean: The output model(s) or model elements(s) that result from executing the transformation.
Note on F47: Toby McClean: This trace is a map of source element(s) + transformation rule to the target element(s)
Note on F48: Toby McClean: So that if the target model already exists that the user can merge the new target model with the existing one
Note on C52: Toby McClean: Not sure that I understand how this one is a M2T requirement. This is actually a requirement on the transformation author.

## D4. M2T-Xpand
Ericsson Requirement |  |  |  |  | OpenSource Tool(s) Evaluated | Criteria |  |  |  | Total Estimated Gap Effort [PM] | Potential Developer Group | Total Requirement Effort for 2011 [PM] | Total Requirement Effort [PM]
Category | Requirement Name | Req. Id | Priority | Detailed capability |  | Functionality |  | Documentation
[6 empty] | Discussion | Est. Effort[PM] | Discussion | Est. Effort [PM]
D. Flexible Content Support 4. Model to Text (M2T) Transformations | Support for generation of source code, documentation and test cases from a model | 4.1 + E-Doc-1 | 10 | Creation of transformation utilities | Xpand/MWE Sphinx | Basic functions exists | 0 |  | 0 | 0 |  | 0 | 11
|  |  | 30 | Allow for the use of name maps |  | Not supported; is possible but not yet implemented as a feature. Estimates are for simple implementation as feature. | 1 |  | 0 | 1
|  |  | 20 | Creation of configuration validation rules |  | Supported | 0 |  | 0 | 0
|  |  | 10 | Definition of configuration/control properties |  | Supported | 0 |  | 0 | 0
|  |  | 10 | Creation of new model transformations and transformation rules |  | Partially supported, UI Support needed | 1 |  | 0 | 1 | itemis
|  |  | 20 | Extend/customize existing transformation |  | Supported | 0 |  | 0 | 0
|  |  | 30 | Control whether a transformation can be extended |  | Not supported | 1 |  | 0 | 1 | itemis
|  |  | 10 | Debugging - breakpoint support |  | Supported | 0 |  | 0 | 0
|  |  | 10 | Debugging - inspecting context |  | Supported | 0 |  | 0 | 0
|  |  | 10 | Debugging - inspecting stack trace |  | Supported | 0 |  | 0 | 0
|  |  | 10 | Debugging - stepping through transformation |  | Supported | 0 |  | 0 | 0
|  |  | 20 | Debugging - conditinal breakpoint |  | Not supported; done in the context of Xtend | 0 |  | 0 | 0
|  |  | 20 | Debugging - expression evaluations |  | Not supported; done in the context of Xtend | 0 |  | 0 | 0
|  |  | 10 | Compilation |  | Partially supported; needs optimization for large models | 2 |  | 0 | 2 | itemis
|  |  | 20 | Profiling and Optimization |  | Partially supported; needs optimization for large models | 4 |  | 0 | 4 | itemis
|  |  | 30 | Refactorings |  | Partially supported; needs optimization for large model2 | 2 |  | 0 | 2 | itemis
|  |  | 10 | Generate HTML |  | Supported | 0 |  | 0 | 0
|  |  |  | Generate PDF |  | N/A | 0 |  | 0 | 0
|  |  |  | Generate Word Document |  | N/A | 0 |  | 0 | 0
|  |  |  | Ability to include diagrams in documents |  | N/A | 0 |  | 0 | 0
|  |  | 10 | Document templates metamodel aware |  | Supported | 0 |  | 0 | 0
|  |  | 10 | Document templates support UML stereotypes |  | Supported | 0 |  | 0 | 0
|  |  | 10 | Document templates support generating for a subset of the model |  | Supported | 0 |  | 0 | 0
|  |  | 10 | Document templates can be invoked in headless mode |  | Supported | 0 |  | 0 | 0
|  |  | 10 | Document templates support SQL like expressions |  | Supported | 0 |  | 0 | 0
|  |  | 10 | Document templates support SQL like queries |  | Supported | 0 |  | 0 | 0
|  |  | 10 | Document templates support SQL like grouping |  | Supported | 0 |  | 0 | 0
|  |  | 10 | Document templates support extensions through Java |  | Supported | 0 |  | 0 | 0
| Ability to select and apply appropriate generation template to one or several models | 4.2 (proposed) | 10 | Define a specific configuration of a code generation, i.e., some sort of launch configuration for running Xpand without MWE |  | Not supported | 1 |  | 0 | 1 |  | 0 | 6
|  |  | 30 | Define a hierarchy of configurations |  | Not supported; Does not fit well into the Xpand context. Needs new concepts and implementation | 1 |  | 0 | 1
|  |  | 30 | Define a name map |  | Supported | 0 |  | 0 | 0
|  |  | 10 | Editor to define a specific configuration of a code generation, i.e., the UI of the Xpand launch configuration |  | Not supported | 0 |  | 0 | 0
|  |  | 10 | Code generation execution provides feedback to user, i.e., progress bar |  | Supported; in form of console logging | 1 |  | 0 | 1
|  |  | 20 | Applying an extended code generation includes the extensions |  | Supported; through extend/customize existing transformation | 0 |  | 0 | 0
|  |  | 10 | Execution from within IDE |  | Partially supported, Creation of launch configurations must be simplified or made avoidable, execution without need for separate workspace must be possible; needs integration with Sphinx service for running code generation from centrally managed models that are already loaded | 3 |  | 0 | 3 | itemis Geensys
|  |  | 10 | Execution from ANT script |  | Supported | 0 |  | 0 | 0
|  |  | 10 | Execution from command line |  | Supported | 0 |  | 0 | 0
|  |  | 10 | Execution through Java API |  | Supported | 0 |  | 0 | 0
| Open, modifiable, and extensible code generation specifications | E-CdGen-1 |  | Nothing to add |  | Supported | 0 |  | 0 | 0 |  | 0 | 0
| Ability to generate code for different target languages | E-CdGen-2 | 10 | Obtain target model(s) and/or text |  | Supported | 0 |  | 0 | 0 |  | 0 | 2
|  |  | 20 | Obtain transformation trace |  | not supported | 2 |  | 0 | 2 | itemis
|  |  |  | Integration with diff/merge |  | N/A | 0 |  | 0 | 0
| Ability to define incremental and scalable code generators and compilations | E-CdGen-4 |  | Not clear what this requirement exactly means |  | N/A | 0 |  | 0 | 0 |  | 0 | 0
| Code generation support for easy debugging of generated code | E-CdGen-6 |  | This is a question of how the code generation templates are designed but not on the technology used for running them. The requirement therefore is deemd as not applicable. |  | N/A | 0 |  | 0 | 0 | 0 | 0 | 0
Note on E4: Toby McClean: Transformation utilities perform routine tasks and facility in the authoring of new transformations. For example, a transformation utlity could check the permissions on the source and targets of the transformation.
Note on E5: Toby McClean: The name map specifies alternate names for target files and folders
Note on E6: Toby McClean: A configuration validation rule(s) ensure that the values for configuration/control properties, input models and target models are valid in the context of the given transformation.
Note on E7: Toby McClean: A configuration or control property allows the transformation user to provide additional information to the transformation in order to control its execution and output. There should be no limitations on the richness of these properties, that is they can be complex structures. The specific values provided to the transformation must be avaialble during the execution of the transformation.
Note on E8: Toby McClean: The definition of the transformation and the rules that compose it should provide the author with some way of controlling the order in which things execute.
Note on E9: Toby McClean: Authoer can add new rules and properties to an existing transformation. Also the ability to replace parts of the transformation.
Note on E10: Toby McClean: This is a flag the user can set to indicate whether the transformation can be extended or not. It is similar to final on a class in Java.
Note on E11: Toby McClean: The ability to set break points in the transformatino that pauses the execution of the tranformation when it reaches that point.
Note on E12: Toby McClean: This allows the transformation other to see the currently values of model elements and properties
Note on E13: Toby McClean: This allows the author to see the current execution stack of the transformation that is executing when it is stopped at a breakpoint.
Note on E14: Toby McClean: Provided functionality like JDT to step through the statements in the transformation.
Note on E33: Toby McClean: A specific configuration of a transformation refers to the ability to define and store values for configuration/control properites, the input model(s)/model element(s) and the target of the transformation.
Note on E34: Toby McClean: A hierarchy of configurations allows the transformation user to define some base configurations that are reused/composed/specialized to create the configurations that are actually used in the execution of a transformation
Note on E35: Toby McClean: The name map specifies alternate names for target files and folders
Note on E36: Toby McClean: In order to make the user experience acceptable a user must be given an editor that is aware of the configuration/control properties, number and type of input model(s) or model element(s) and the number and type of output model(s)
Note on E37: Toby McClean: This for example can be a progess bar that lets the user know what it is currently doing
Note on E38: Toby McClean: When the user applies a transformation like generate C++ that the transformation takes into account the extensions that have been applied to it. That way a user does not have to know the structure of the transformation extensions.
Note on E39: Stephan Eberle: Includes things like actions for invoking configured transformations on model elements or resources in the workspace, threadsafe execution of transformation, operation on already loaded and centrally managed models rather than loading models for each transformation run spearately, transformation progress indication through Eclipse progress view and/or ProgressService dialog, automatic refresh of workspace and view to display model resources/elements resulting from transformation, creation of error markers on input files indicating problems encountered during transformation, label decorator for advertising such problems in tree-based views. As more or less the same functions are needed for integrating plenty of other technologies, I consider that capability should be provided once for all by Sphinx rather than individually by each particular technology.
Note on C44: Toby McClean: I think that this can be collapsed into 4.1
Note on E46: Toby McClean: The output model(s) or model elements(s) that result from executing the transformation.
Note on E47: Toby McClean: This trace is a map of source element(s) + transformation rule to the target element(s)
Note on E48: Toby McClean: So that if the target model already exists that the user can merge the new target model with the existing one
Note on C52: Toby McClean: Not sure that I understand how this one is a M2T requirement. This is actually a requirement on the transformation author.

## E1. Project Tracking
Requirement |  |  |  |  | OpenSource Tool(s) Evaluated | Criteria |  |  |  | Total Estimated Gap Effort [PM] | Potential Developer Group | Total Requirement Effort for 2011 [PM] | Total Requirement Effort [PM]
Category | Requirement Name | Req. Id | Priority | Detailed capability |  | Functionality |  | Documentation
[6 empty] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM]
E. Governance 1. Tracking and managing project status | Ability to define which project information is to be tracked and how it is to be reported | 1.1 | 30 | Seems to be a requirement without any particular relation to modeling; it therefore would be inappropriate to add corresponding services to the modeling platform; no effort estimates will be provided unless we can get some more specific use cases which illustrate the modeling-specific aspects to be addressed |  |  | 0 |  | 0 | 0 |  | 0 | 0
| Capability to determine current status of key project indicators | 1.2 a) | 30 | Seems to be a requirement without any particular relation to modeling; it therefore would be inappropriate to add corresponding services to the modeling platform; no effort estimates will be provided unless we can get some more specific use cases which illustrate the modeling-specific aspects to be addressed |  |  | 0 |  | 0 | 0 |  | 0 | 0
| Capability to determine how those evolved over time (project history) | 1.2 b) | 30 | Seems to be a requirement without any particular relation to modeling; it therefore would be inappropriate to add corresponding services to the modeling platform; no effort estimates will be provided unless we can get some more specific use cases which illustrate the modeling-specific aspects to be addressed |  |  | 0 |  | 0 | 0 |  | 0 | 0
| Support for raising warnings when certain critical situations or events occur | 1.2 c) | 30 | Seems to be a requirement without any particular relation to modeling; it therefore would be inappropriate to add corresponding services to the modeling platform; no effort estimates will be provided unless we can get some more specific use cases which illustrate the modeling-specific aspects to be addressed |  |  | 0 |  | 0 | 0 |  | 0 | 0

## E2. Toolset Management
Requirement |  |  |  |  | OpenSource Tool(s) Evaluated | Criteria |  |  |  | Total Estimated Gap Effort [PM] | Potential Developer Group | Total Requirement Effort for 2011 [PM] | Total Requirement Effort [PM]
Category | Requirement Name | Req. Id | Priority | Detailed capability |  | Functionality |  | Documentation
[6 empty] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM]
E. Governance 2. Toolset configuration and management | Support for constitution and configuration of new tools suites for use by a team or enterprise | 2.1 | 30 | Means to formally describe (model) the composition of a tool suite including necessary authoring tool support | MTF P2 Sphinx |  | 12 |  |  | 12 |  | 0 | 28
|  |  | 30 | Means to formally describe (model) the configuration of the tools including necessary authoring tool support |  |  | 6 |  |  | 6
|  |  | 30 | Import of a configuration description and automated composition and configuration of corresponding tool suite |  |  | 6 |  |  | 6
|  |  | 30 | Report of the current configuration of a tool suite by generating of a human readable configuration description |  |  | 1 |  |  | 1
|  |  | 30 | Support to test a new configurations before introduction in operational environment (e.g. completness of dependencies, exlusion of tool version conflicts, etc.) |  |  | 3 |  |  | 3
| Support for adding new tools/capabilities to existing tools suites | 2.2 | 30 | Automatic management of dependencies between tools when updating existing ones or installing new ones (e.g., automatic installation of dependent tools, detection of missing dependencies) | MTF P2 Sphinx |  | 2 |  |  | 2 |  | 0 | 2
|  |  | 30 | Support for tests of compatibility with the existing tools |  | Covered by "Support to test a new configurations ...", see above | 0 |  |  | 0
| Support for controlled update of individual tools/capabilities in existing tools suites | 2.3 | 30 | Support for the management of the users and user profiles and automated installation/configuration of tools corresponding to the users' role in their tool sets | MTF P2 Sphinx |  | 12 |  |  | 12 |  | 0 | 12

## F. Host and Target Debugging
Requirement |  |  |  |  | OpenSource Tool(s) Evaluated | Criteria | [13 empty] | Total Estimated Gap Effort [PM] | Potential Developer Group | Total Requirement Effort for 2011 [PM] | Total Requirement Effort [PM]
Category | Requirement Name | Req. Id | Priority | Detailed capability |  | Functionality |  | Customizability |  | Extensibility |  | Scalability |  | Usability |  | Interoperability |  | Documentation
[6 empty] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM] | Discussion | Est. Effort [PM]
F. Host and Target Debugging | Support code generation and debugging on different target platforms | E-CdGen-3 | 20 | Support debugging at the model level a system running on a target platform | MXF | Not supported | 24 | [12 empty] | 24 |  | 0 | 24
| Model-level simulation with debug support | E-DbgSim-1 | 20 | Support debugging at the model level of a simulation of a system | MXF | Not supported | 24 | [12 empty] | 24 |  | 0 | 24
| Debug of individual instances (vs just classes) | E-DbgSim-2 | 20 | Support debugging of individual instances of elements in a model | MXF | Not supported | 6 | [12 empty] | 6 |  | 0 | 6
| Store and restore of debug/test harnesses | E-DbgSim-3 | 20 | Support storing state of debug/test harnesses | MXF | Not supported | 6 | [12 empty] | 6 |  | 0 | 9
|  |  | 20 | Support restoring state of debug/test harnesses |  | Not supported | 3 | [12 empty] | 3
| Simulation/execution trace record and replay | E-Dbg-Sim-4 | 20 | Record execution of system | MXF | Not supported | 4 | [12 empty] | 4 |  | 0 | 10
|  |  | 20 | Record simulation of system |  | Not supported | 0 | [12 empty] | 0
|  |  | 20 | Replay recording |  | Not supported | 6 | [12 empty] | 6